## Test environment
Alpha testing for Skybot portal v 3.0
Project name: |  | Skybot portal
Testing start date: |  | 2024-09-14
Testing end date: |  | 2024-09-15
Performed by: |  | Bohdan Prykhodchenko
Iteration: |  | 1
Description of the testing environment required to perform Alpha testing of the Skybot portal v 3.0
Software | OS | Browser | Device | Hardware | Network connection | Test Data | Requirements | Access | Involved staff
| Windows 11 Pro 23H2 64bit | Chrome128.0.6613.120 | Laptop Dell Latitude 7490 | CPU Intel i5-8350U, GPU Intel UHD Graphics 620, 16Gb RAM, SSD hard drive, mouse, 27" display with 2560 x 1440 (2K) resolution | fixed lan-wifi network up to 200 Mbit/s | https://prometheusqastage3.wixsite.com/skybot | Оновлені вимоги до порталу | Hosting admin panel | Testing team O.Solodka
| Android 13 | Firefox 129.0.2 | Smartphone Xiaomi Mi 11 Lite 5G | CPU Qualcomm Snapdragon 780G, GPU Adreno 642, 6Gb RAM, 6.55" display with 2400x1080 (FullHD) resolution | 4G mobile network Kyivstar | Login |  | Portal admin panel | Stakeholders B. Prykhodchenko
| Android 9 | Firefox 129.0.2 | Smartphone Xiaomi Mi A1 | CPU Qualcomm Snapdragon 625, GPU Adreno 506, 4Gb RAM, 5.5" display with 1920x1080 (FullHD) resolution | 4G mobile network Kyivstar | 13102020kh@ukr.net |  | Domain admin panel
[6 empty] | Password |  | Portal's email service
[6 empty] | Ta12345ra |  | Portal's database
Portal output data
The structure of Alpha testing for Skybot portal v 3.0
Web hosting |  | Verifies that the web hosting is fast, stable and secure as required
Mobile version |  | Verifies that the mobile version is capable of working on mobile devices and supports all the necessary functionality
Design |  | Verifies that the Design is convenient and intuitive with the ability to update
Frontend |  | Verifies that the Frontend side of the portal is stable and ensures smooth operation of the portal
Backend |  | Verifies that the Backend is reliable, ensures continuous operation of the portal and provides data processing and interaction with the frontend
Purchase |  | Verifies that the user can make a purchase
Security |  | Verifies that the portal provides a high level of security for users during registration, authorization and making payments
Product page |  | Verifies that the product pages contains information about each model of electric transport with a detailed description
Test-drive |  | Verifies that the portal provide users with the opportunity to easily and conveniently sign up for a test drive of the selected model of electric transport through the web portal
Service booking |  | Verifies that the portal provides users with a convenient and quick appointment for service or repair at a service center after purchasing a vehicle on the web portal
Reviews |  | Verifies that the user can leave and view the reviews of the products
Recommendations |  | Verifies that the user can receive a personalized recommendations for electric transport products
Videos |  | Verifies that the user can view video reviews of products (models of electric vehicles), integrated videos from popular video hosting platforms
Analytics |  | Verifies that the portal provides necessary infrastructure and integrations to use analytics tools on the portal to collect, analyze and use data to improve operations and user experience
Summary |  | Summary of the acceptance test
Please note that the test overview is located at the bottom of the each page

## Web hosting
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
1.Fast, stable, and secure web hosting | Fast Web Hosting | The portal must load quickly for users during normal and peak traffic conditions | 1. Access to performance testing tools (e.g., Google PageSpeed, GTmetrix). 2. Internet connection is stable. | 1. Open the portal during off-peak hours. 2. Measure page load time. 3. Open the portal during peak hours. 4. Measure page load time. | The portal should load in less than 2 seconds under both off-peak and peak traffic conditions. |  | High
| Stable Web Hosting | The portal must remain stable and responsive under high user loads | 1. Load testing tools available (e.g., Apache JMeter, LoadRunner). 2. Server monitoring setup | 1. Simulate high traffic using load testing tools. 2. Gradually increase the number of users. 3. Monitor server response times and uptime. | The portal should remain stable with no downtime or significant performance issues as user load increases
| Scalable Web Hosting | The portal must scale effectively to handle increased user traffic | 1. Load testing setup to simulate varying user numbers. 2. Monitoring tools in place. | 1. Gradually increase the simulated user traffic in a load testing tool. 2. Observe the portal's performance (load time, response time) as the traffic scales. | The portal should automatically scale up to handle increased user traffic without affecting performance (page load times should remain consistent)
| Support for High Visitors | The web hosting must support a large number of concurrent visitors | 1. Hosting infrastructure setup for high traffic. 2. Monitoring system resources. | 1. Simulate maximum expected concurrent users. 2. Monitor hosting performance. 3. Analyze any downtimes or errors encountered during the test. | The portal should be able to handle the maximum number of concurrent visitors without crashing or significantly slowing down. Resources should be optimized.
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for speed, stability and support of the hosting, also there is a scalability tests. which is an additional part of the stability requirements. However, a security test should be added to cover the security requirements. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. In case of issues, there are comments with detailed information. Tests are estimated by priority only by division of requirements, not each test separately. Also there is a recommendation for Steps To Execute to mention the tools and the procedure to provide described test steps. |  |  | 100%

## Mobile version
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
2. Mobile version that works quickly on mobile devices | Fast Mobile Performance | The mobile version of the portal must load quickly and perform smoothly on mobile devices | 1. Mobile devices with varying OS versions (e.g., Android, iOS) are available. 2. Stable internet connection on mobile devices. 3. Performance testing tools for mobile. | 1. Access the portal on a mobile device. 2. Measure the time it takes for the mobile version to load. 3. Navigate through various sections of the portal. | The mobile version should load within 2-3 seconds and allow for smooth navigation without noticeable lag or delays. |  | High
| Responsive Design | The mobile version must adapt correctly to different screen sizes and orientations | 1. Multiple mobile devices with different screen sizes and resolutions. 2. Browsers are up to date. | 1. Access the portal on devices with different screen sizes (e.g., smartphone, tablet). 2. Rotate the devices between portrait and landscape orientations | The layout should adjust seamlessly to different screen sizes and orientations, with no elements overlapping or misaligned
| Touchscreen Usability | The portal must be easy to navigate using touchscreen interactions | 1. Access to various mobile devices with touchscreen capability | 1. Access the portal on a touchscreen device. 2. Navigate through the portal using common gestures (swipe, tap, pinch-to-zoom) | The portal should respond accurately and promptly to all touchscreen interactions, with intuitive and smooth gesture controls
| Efficient Mobile Data Usage | The mobile version should minimize data consumption to ensure a good user experience on mobile networks | 1. Mobile data monitoring tools available. 2. Access to mobile networks with varying speeds (e.g., 4G, 5G) | 1. Access the portal using mobile data on a mobile device. 2. Monitor data usage while navigating through different sections of the portal. | The portal should use a minimal amount of data, optimizing images and content to ensure fast loading even on slower mobile networks
| Compatibility | The mobile version must be compatible with various mobile operating systems and browsers | 1. Devices with different mobile OS (e.g., iOS, Android). 2. Multiple mobile browsers (e.g., Safari, Chrome, Firefox) | 1. Access the portal on devices with different operating systems. 2. Test the portal on multiple mobile browsers. 3. Check for any compatibility issues. | The portal should function consistently across different mobile operating systems and browsers, with no major display or performance issues
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for performance, responsiveness, usability, efficienty and compatibility of the mobile version of the portal. This is quite enough to check the mobile version of the portal. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. In case of issues, there are comments with detailed information. Tests are estimated by priority only by division of requirements, not each test separately. Also there is a recommendation for Steps To Execute to mention the tools and the procedure to provide described test steps. |  |  | 100%

## Design
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
3. A user-friendly, intuitive design with the ability to update it: | User-Friendly Design | The portal must have an intuitive and easy-to-navigate design for all user types | 1. Access to the portal on multiple devices (desktop, mobile, tablet). 2. Access to users for feedback. | 1. Access the portal on different devices. 2. Perform key tasks (e.g., finding a product, making a purchase, contacting support). 3. Collect user feedback. | Users should be able to easily navigate the portal, completing tasks without confusion. Feedback should be positive regarding the ease of use |  | High
| Clear and Understandable UI | The design should present information clearly, with consistent and readable elements | 1. Access to devices with different screen sizes and resolutions. 2. Access to users with varying levels of tech proficiency. | 1. Access the portal and review the placement and readability of text, buttons, and images. 2. Test with users of different tech skill levels | All users should be able to understand and interact with the design without difficulty, with clear text, well-placed buttons, and accessible navigation
| Design Update Capability | The portal must allow for easy updates and changes to the design without major disruption | 1. Access to the content management system (CMS) or design interface. 2. Backup of current design. | 1. Log in to the CMS or design interface. 2. Make a design change (e.g., update a banner, change a color scheme). 3. Publish the update and check the portal. | The design should be easily updated through the CMS, with changes reflecting instantly on the portal without disrupting user experience or causing downtime
| Consistent Design Across Pages | The design should be consistent across all pages of the portal | 1. Access to all sections and pages of the portal. 2. List of design standards (e.g., fonts, colors). | 1. Navigate through all pages of the portal. 2. Compare each page against the design standards list to ensure consistency. | All pages should have a consistent design in terms of fonts, colors, and layout, maintaining a uniform look and feel throughout the portal
| Responsive Design Updates | Design changes should maintain responsiveness and usability on all devices. | 1. Access to devices with different screen sizes. 2. Design update tools available. | 1. Implement a design update (e.g., change header layout). 2. Access the portal on various devices and screen sizes. 3. Test responsiveness after the update | The portal should remain responsive and user-friendly on all devices after the design update, with no issues in navigation or display.
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for comfort, understandable and clear for users design, possibilities to upgrade, responsivness and consistency of the portal's design. Also there is a compatibility test, which is an important part of the adaptability of the portal. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. In case of issues, there are comments with detailed information. Tests are estimated by priority only by division of requirements, not each test separately. Also there is a recommendation for Steps To Execute to mention the tools and the procedure to provide described test steps. |  |  | 100%

## Frontend
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
4. Frontend stability | Stable Frontend Operation | The frontend must provide stable and uninterrupted performance for all users | 1. Access to different devices (desktop, mobile) and browsers (Chrome, Firefox, Safari, Edge). 2. A reliable network connection. 3. Monitoring and testing tools (e.g., BrowserStack, Lighthouse). | 1. Access the portal on different devices and browsers. 2. Perform typical user actions (login, navigation, transactions). 3. Monitor frontend stability, response time, and resource usage. | The frontend operates smoothly without crashes or slowdowns, maintaining stable performance across all tested devices and browsers |  | High
| Performance Optimization | The frontend must be optimized for resource usage, ensuring fast load times and efficient operation | 1. Access to web performance monitoring tools (e.g., Google Lighthouse, WebPageTest). 2. A CDN and load balancing setup. 3. Pre-configured caching mechanisms | 1. Load the portal on various devices and measure load times. 2. Inspect network activity for the number of server requests and the use of asynchronous loading. 3. Test repeat page loads to verify caching effectiveness. 4. Simulate high traffic to evaluate CDN and load balancing efficiency | 1.Minimized files reduce the number of server requests. 2. Asynchronous loading improves initial load times. 3. Caching effectively reduces load times for repeat visits. 4. CDN and load balancing ensure even distribution of traffic with no performance degradation under load.
| Cross-Browser Compatibility | The frontend must be compatible across major browsers and their versions | 1. Access to testing tools (e.g., BrowserStack, Sauce Labs). 2. Multiple versions of Chrome, Firefox, Safari, and Edge available for testing | 1. Load the portal in different browsers and versions. 2. Execute a series of user actions (login, form submissions, navigation). 3. Use testing tools to verify consistent behavior and appearance across browsers. | The frontend renders and functions consistently across all tested browsers, with no visual or functional discrepancies
| Security | The frontend must be secure against common web vulnerabilities like XSS and CSRF. | 1. Access to security testing tools (e.g., OWASP ZAP, Burp Suite). 2. User accounts with different levels of access. 3. Configured authentication mechanisms and security tokens. | 1. Perform XSS and CSRF attacks using security testing tools. 2. Attempt unauthorized access to restricted areas. 3. Monitor the behavior of security mechanisms (e.g., token validation). | 1. The frontend effectively prevents XSS attacks by sanitizing input. 2. CSRF protection is active, and malicious requests are blocked. 3. Unauthorized access attempts are denied, and user data remains secure.
| Accessibility & Usability | The frontend must be accessible and user-friendly for all users, including those with disabilities | 1. Access to accessibility testing tools (e.g., Axe, WAVE). 2. Knowledge of WCAG guidelines. 3. Availability of users with different abilities for testing | 1.Evaluate the portal against WCAG guidelines using testing tools. 2. Check for proper use of ARIA attributes. 3. Conduct usability tests with users to gather feedback. 4. Simulate scenarios with screen readers and keyboard navigation. | The frontend meets accessibility standards, with proper ARIA attributes, and provides a user-friendly experience for all users
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for stability, performance, compatibility, safety and accessability of the portal, which are the main frontend requirements. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. In case of issues, there are comments with detailed information. Tests are estimated by priority only by division of requirements, not each test separately. Also there is a recommendation for Steps To Execute to mention the tools and the procedure to provide described test steps. |  |  | 100%

## Backend
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
5. Reliable Backend | Reliable Backend Operation | The backend must provide reliable and uninterrupted service, data processing, and interaction with the frontend | 1. Access to monitoring tools (e.g., Prometheus, Grafana). 2. CI/CD pipeline configured (e.g., Jenkins, GitLab CI). 3. Backup and recovery plan in place. 4. Security protocols set up (e.g., JWT, SSL/TLS). | 1. Deploy the backend and monitor the stability of services using monitoring tools. 2. Check logs for critical events and errors. 3. Run automated regression tests after updates. 4. Simulate data recovery scenarios using backups. 5. Test the authentication and authorization processes using JWT and OAuth. 6. Evaluate the backend's performance under varying loads to check scalability and auto-scaling features. 7. Verify the application of security patches and software updates. | 1. Backend services remain stable and responsive, with no downtime or critical errors. 2. Logs accurately record all significant events, errors, and system interactions. 3. Regression tests pass, confirming that updates do not introduce new issues. 4. Data recovery is successful without loss of information. 5. Authentication and authorization mechanisms function securely. 6. Backend scales appropriately to handle increased loads. 7. Security updates and patches are applied promptly without affecting backend stability. |  | High
| Performance and Stability | The backend must handle resource optimization, load distribution, and maintain stability under high traffic conditions | 1. Access to a test environment with load balancing and CDN enabled. 2. Tools for stress and performance testing. | 1. Conduct performance tests to simulate high traffic and evaluate the backend's response time and resource usage. 2. Check how the backend distributes loads across servers using load balancing. 3. Measure the effectiveness of caching and CDN in reducing load times. | The backend remains stable under high traffic, effectively distributing loads and maintaining optimal performance. Resource usage is optimized, and load times are minimized
| Security Measures | The backend must be secure against attacks, ensuring safe data transmission and protection against vulnerabilities. | 1. Security testing tools (e.g., OWASP ZAP, Burp Suite). 2. Secure connections configured (e.g., SSL/TLS). 3. Regular security updates scheduled. | 1. Perform security tests to detect potential vulnerabilities like SQL injections or XSS. 2. Test data transmission security by inspecting SSL/TLS encryption. 3. Verify the timely application of security updates and patches. | The backend is secure, preventing unauthorized access, SQL injections, and other vulnerabilities. Data is safely transmitted with SSL/TLS, and security updates are regularly applied
| Scalability and Maintenance | The backend must be scalable and maintainable, supporting microservices architecture and horizontal scaling | 1. Backend architecture set up with microservices and orchestration tools (e.g., Kubernetes). 2. Auto-scaling configurations enabled | 1. Test the backend's microservices to ensure they operate independently and efficiently. 2. Simulate increased traffic to trigger auto-scaling mechanisms and assess their effectiveness. 3. Review the orchestration of services for consistency and reliability | Microservices function independently without issues, auto-scaling adjusts resources as needed, and the backend is easily maintainable and scalable
| Support and Documentation | The backend must provide 24/7 technical support and thorough documentation | 1. Availability of a support team. 2. Comprehensive documentation for backend services | 1. Contact technical support with a critical issue and evaluate response time and resolution effectiveness. 2. Review the backend documentation for completeness and clarity. | Technical support is available 24/7, promptly addressing critical issues. Documentation is thorough, accurate, and easy to understand, covering all necessary backend operations and configurations
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for reliability, performance, stability, security, scalability, maintance and support of the portal - the main divisions of the Backend rewuirements. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. In case of issues, there are comments with detailed information. Tests are estimated by priority only by division of requirements, not each test separately. Also there is a recommendation for Steps To Execute to mention the tools and the procedure to provide described test steps. |  |  | 100%

## Purchase
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
6. Fast order processing | Speed and Simplicity of Checkout | The order checkout process should be quick, intuitive, and require minimal steps to complete the purchase | 1. The website has a checkout function. 2. A test user account is available. | 1. Go to the product page and add a product to the cart. 2. Proceed to checkout. 3. Complete the checkout process on a single page (one-page checkout). 4. Ensure auto-fill for user details (name, address) based on previously entered data. 5. Try to checkout as a guest without creating an account. 6. Enter all data and complete the checkout. | The checkout process is completed quickly on one page. Auto-fill works correctly. Guest checkout is possible without account creation. The order is successfully completed without delays |  | High
| Transparency of Process | Display a clear summary of the order and provide a progress bar for users | 1. The website has a cart review feature. 2. Multiple items are added to the cart. | 1. Navigate to the cart review page. 2. Ensure the order summary displays all items, quantities, prices, and the total amount. 3. Modify the quantity of items in the cart and verify the total amount updates. 4. Proceed to checkout and check for a progress bar. | The order summary accurately shows all items and costs. Cart changes are updated immediately. The progress bar clearly indicates the steps and remaining stages of the process.
| Security of Checkout | The checkout process must be secure and offer multiple payment options. | 1. SSL/TLS is configured for secure connections. 2. Multiple payment gateways (credit cards, PayPal) are integrated. | 1. Proceed to the order checkout. 2. Ensure the connection is secure (HTTPS). 3. Select a payment option (e.g., credit card) and complete the payment. 4. Verify the receipt of an order confirmation email. | Payment is processed over a secure connection. The user receives an order confirmation email with details
| User Support | Provide online chat or contact information for quick support during the checkout process. | 1. The website has integrated online chat or contact information. | 1. Navigate to the checkout page. 2. Enter incorrect data (e.g., invalid email format). 3. Verify if error messages are displayed. 4. Attempt to contact support via online chat or phone number for resolution. | The user receives immediate error messages for incorrect data entry. Online chat or contact information is available for quick support
| Mobile Optimization | The checkout process should be optimized for mobile devices with user-friendly forms and elements | 1. Mobile device with internet access. 2. Responsive design of the website | 1. Open the website on a mobile device. 2. Add a product to the cart and proceed to checkout. 3. Enter data using mobile forms. 4. Ensure all elements (buttons, input fields) are usable on the mobile device. 5. Complete the checkout process on the mobile device. | The checkout process is user-friendly on mobile devices, with all forms and elements optimized for mobile use. The order is successfully completed from a mobile device without issues
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for speed and simplicity of Checkout, transparency, security, user support and mobile optimization of the portal, which are the main divisions of the Order Processing requirements More tests can be added only with additional access to the porta's documentation. admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. In case of issues, there are comments with detailed information. Tests are estimated by priority only by division of requirements, not each test separately. Also there is a recommendation for Steps To Execute to mention the tools and the procedure to provide described test steps. |  |  | 100%

## Security
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
7. User Security and Secure Payments | User Security and Secure Payments | Ensure high security for user accounts and secure payment transactions. | 1. The portal is operational. 2. A test user account is available. 3. The payment gateway is integrated for testing. | Authentication and Authorization: 1. Attempt registration with a weak password. 2. Verify system enforces strong password rules. 3. Enable two-factor authentication (2FA) for a user account. 4. Try logging in with and without 2FA. 5. Inspect encrypted data transmission. Secure Payments: 6. Complete a test payment. 7. Ensure SSL/TLS is used for payment processing. 8. Verify PCI DSS compliance. Monitoring and Incident Detection: 9. Confirm security monitoring systems are active. 10. Trigger a security alert and check for automatic notifications. User Experience: 11. Access and review the privacy policy. 12. Check the terms of use and data protection details. | 1. The system enforces strong password policies. 2. 2FA is properly implemented and functioning. 3. Data is transmitted using encryption. Secure Payments: 4. SSL/TLS is applied for secure payment. 5. Payment processing adheres to PCI DSS standards. Monitoring and Incident Detection: 6. Security monitoring tools are operational. 7. Alerts are automatically generated for suspicious activities. User Experience: 8. Privacy policy and terms of use are accessible and detailed. |  | High
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for User Security and Secure Payments, which are the important part of the security requirements. It is realized by e2e test scenario, and very easy to provide, all needed parts of requirements are covered. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. In case of issues, there are comments with detailed information. However there is a recommendation for Steps To Execute to mention the tools and the procedure to provide described test steps. |  |  | 100%

## Product page
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
8. Detailed Information for Each Electric Vehicle Model | Detailed Information for Each Electric Vehicle Model | Ensure that each electric vehicle model on the portal has detailed and informative descriptions, including technical specifications, features, and other relevant information. | 1. The portal is operational. 2. Electric vehicle models are added to the database. 3. The portal’s UI is designed to display detailed information | 1. Navigate to the Electric Vehicles Section: 1.1. Go to the section listing all electric vehicle models. 1.2. Select a specific model. 2. Check Basic Information: 2.1. Verify that the model’s full name and category (e.g., electric scooter) are displayed. 3. Check Description and Features: 3.1. Review the detailed description, ensuring it covers all technical specifications like weight, dimensions, battery type, range per charge, and charging time. 3.2. Ensure that the description highlights unique features and functionalities. 4. Visual Representation: 4.1. Check that high-quality images and videos from different angles are provided. 5. User Interaction: 5.1. Verify the functionality allowing users to leave reviews and comments. 6. Update Verification: 6.1. Confirm that the information is up-to-date, reflecting any recent updates or releases. | 1. Each electric vehicle model is listed with a clear name and category. 2. The model’s page displays a comprehensive description, covering all key specifications and unique features. 3. High-quality images and videos are provided, showing the model from various angles. 4. The user is able to leave reviews and comments. 5. The information is current and accurately reflects the latest updates and releases. |  | High | Successfully displays full technical details and images
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for Detailed Information for Each Electric Vehicle Model. It is realized by check list and very easy to provide, all needed parts of requirements are covered. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. |  |  | 100%

## Test-drive
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
9. Test Drive Booking | Test Drive Booking from the Portal | Ensure users can book a test drive for electric vehicles directly from the portal. | 1. The portal is operational. 2. Test drive options are configured in the system. 3. Users are registered and logged into the portal. 4. Test drive schedules are available. | 1. Navigate to the Test Drive Section: 1.1. Go to the section listing all available electric vehicle models. 1.2. Select a specific model. 2. Access the Test Drive Booking Feature: 2.1. Click on the "Book a Test Drive" button. 3. Fill in Booking Details: 3.1. Provide required personal information (name, contact details). 3.2. Select preferred date and time for the test drive. 3.3. Choose the location if applicable. 4. Submit the Booking: 4.1. Review the details and submit the test drive request. 5. Confirm Booking: 5.1. Check for confirmation of the booking request. 5.2. Review any follow-up communication sent via email or shown on-screen | 1. Users can access the test drive booking option for any electric vehicle model. 2. The booking form accepts necessary details such as personal information, date, time, and location. 3. Upon submission, the system confirms the booking and provides a summary. 4. A confirmation message is displayed, and an email is sent with the booking details and instructions. |  | High
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the Test Drive Booking from the Portal. It is realized by check list and very easy to provide, all needed parts of requirements are covered. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. |  |  | 100%

## Service booking
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
10. Service Center Booking | Service Center Booking for Purchased Models | Ensure users who have purchased a model can book a service center appointment through the portal. | 1. The portal is operational. 2. Users are registered, logged in, and have purchased a model. 3. Service center schedules are available. | 1. Navigate to the Service Center Section: 1.1. Log into the portal with a user account that has purchased a model. 1.2. Go to the "My Purchases" or "Service Center" section. 2. Access the Service Booking Feature: 2.1. Select the purchased model from the list. 2.2. Click on "Book a Service Appointment" or similar option. 3. Fill in Service Booking Details: 3.1. Choose the issue or type of service required. 3.2. Select preferred date, time, and service center location. 4. Submit the Booking: 4.1. Review the details and submit the service request. 5. Confirm Booking: 5.1. Verify the confirmation of the service booking. 5.2. Review any follow-up communication provided via email or on-screen. | 1. Users can access the service booking option for any purchased model. 2. The booking form accepts necessary details such as issue type, date, time, and location. 3. Upon submission, the system confirms the booking and provides a summary. 4. A confirmation message is displayed, and an email is sent with the service appointment details and instructions. |  | High
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for Service Center Booking for Purchased Models. It is realized by check list and very easy to provide, all needed parts of requirements are covered. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. |  |  | 100%

## Reviews
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
11. Product Reviews | Product Reviews | Ensure users can submit and view reviews for products on the portal. | 1. The portal is operational. 2. The user is registered and logged into the portal. 3. The product page is accessible. | 1. Navigate to Product Page: 1.1. Log into the portal with a registered user account. 1.2. Go to the product page for a specific item. 2. Access Review Section: 2.1. Scroll down to the "Reviews" section. 2.2. Click on "Write a Review" or similar option. 3. Submit a Review: 3.1. Rate the product using the rating system provided (e.g., 1-5 stars). 3.2. Write a review in the provided text box. 3.3. Optionally, upload photos or videos related to the product. 3.4. Submit the review. 4. View Submitted Reviews: 4.1. Refresh the product page. 4.2. Scroll to the "Reviews" section to view the newly submitted review along with existing reviews. | 1. Users can access the review submission form. 2. The system accepts a rating, text review, and optional media. 3. Upon submission, the review is displayed under the product's "Reviews" section. 4. The newly submitted review appears alongside existing reviews and is properly formatted. |  | High
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for Product Reviews. It is realized by check list and very easy to provide, all needed parts of requirements are covered. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. In case of issues, there are comments with detailed information. |  |  | 100%

## Recommendations
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
12. Personalized Product Recommendations | Providing personalized product recommendations | Ensure the portal provides personalized product recommendations based on the user's browsing history, preferences, and past purchases | 1. The portal is operational. 2. The user is registered and logged into the portal. 3. The user has a history of browsing or purchases. | 1. Log into the Portal: 1.1. Log into the portal with a registered user account. 2. View Homepage: 2.1. After login, view the homepage or a product page. 3. Access Recommendations Section: 3.1. Scroll to the "Recommended for You" section. 4. Interact with Recommendations: 4.1. Review the list of recommended products. 4.2. Click on a recommended product to view its details. 5. Validate Recommendations: 5.1. Check that the recommendations are relevant to the user's previous interactions on the site (e.g., similar categories, brands, or types of products previously viewed or purchased). | 1. The "Recommended for You" section is visible on the homepage or relevant product pages. 2. The recommended products are relevant to the user's past interactions. 3. Clicking a recommended product leads to the correct product details page. |  | High
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for Providing personalized product recommendations. It is realized by check list and very easy to provide, all needed parts of requirements are covered. More tests can be added only with additional access to the porta's documentation. admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. |  |  | 100%

## Videos
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
13. Integration with Video Hosting | Integration with Video Hosting for Product Reviews | Ensure the portal integrates with a video hosting platform to allow users to view video reviews of products/models. | 1. The portal is operational. 2. The user is logged into the portal. 3. Video reviews for products/models are available on the video hosting platform. 4. The video hosting service is properly integrated with the portal. | 1. Log into the Portal: 1.1. Log into the portal with a registered user account. 2. Navigate to a Product Page: 2.1. Search for or select a product/model to view its details. 3. View Video Review: 3.1. Scroll down to the "Video Reviews" section on the product page. 3.2. Click the play button on a video review. 4. Interact with Video Player: 4.1. Watch the video review in the embedded player. 4.2. Use player controls (play, pause, volume, fullscreen) as needed. | 1. The "Video Reviews" section is visible on the product page. 2. The video reviews are correctly embedded and can be played directly on the portal. 3. The video plays smoothly without errors. 4. Player controls function as expected (play, pause, volume, fullscreen). |  | High
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for Integration with Video Hosting for Product Reviews. It is realized by check list and very easy to provide, all needed parts of requirements are covered. More tests can be added only with additional access to the porta's documentation. admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. In case of issues, there are comments with detailed information. |  |  | 100%

## Analytics
Requirement | Acceptance Criteria or Requirement | Description | Preconditions/Test Data | Steps To Execute | Expected Results | Pass/Fail | Priority | Comments/Notes
14. Technical Feasibility of Implementing Analytics Tools | Technical Feasibility of Implementing Analytics Tools | Ensure that the portal can integrate and use analytics tools to track user behavior, sales data, and other key metrics. | 1. The portal is fully operational. 2. The analytics tool is set up and accessible. 3. Proper permissions are granted for analytics data collection. 4. The analytics tracking code is integrated into the portal. | 1. Access the Portal: 1.1. Log into the portal as an admin. 2. Verify Analytics Integration: 2.1. Navigate to several pages of the portal (e.g., home, product pages, checkout page). 2.2. Perform various actions (e.g., add items to cart, make a purchase). 3. Check Analytics Dashboard: 3.1. Log into the analytics tool’s dashboard. 3.2. Verify that the data from the user actions is being accurately recorded and displayed. | 1. Analytics tool is correctly integrated into the portal. 2. User interactions (page views, clicks, purchases) are accurately tracked. 3. Analytics data appears in the dashboard in near real-time. 4. No errors or delays in data collection and reporting. |  | High
Testing review:
Coverage |  |  | Completeness of tests |  |  | Accuracy of tests
This tests covers the requirements for Implementing Analytics Tools. It is realized by check list and very easy to provide, all needed parts of requirements are covered. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team |  |  | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. |  |  | 100%

## Summary
Summary of the Alpha testing
Acceptance Testing Report for Skybot Web Portal Version 3.0.0 Date: [03.09.2024-08.09.2024] Project: Skybot Web Portal Version 3.0.0 Tester: [O.Solodka] Test Phase: Acceptance Testing Total Requirements Tested: 14 Requirements Passed: 6 Requirements Failed: 8 Overview The purpose of this report is to provide a summary of the acceptance testing conducted for the Skybot Web Portal. The testing was based on 14 key client requirements. Out of these, 6 requirements have been successfully met, while 8 did not pass. Several critical functionalities remain incomplete, severely impacting the user experience. Critical Issues Identified Several critical requirements were not fulfilled, which could severely impact the user experience and the commercial functionality of the portal: User Cannot Place an Order (R6): The checkout process fails to complete due to an error at the payment processing stage. Urgent attention required to fix this, as it directly affects the sales process. Booking a Test Drive Fails (R9): Users are unable to schedule test drives as the booking form does not submit. High priority fix, as this is a key feature for user engagement. Service Appointment Scheduling Not Functional (R10): Users cannot book appointments for service and maintenance. This negatively affects post-purchase customer support, a vital feature for long-term customer retention. Payment Gateway Issues (R7): The payment process is not complete, affecting users’ ability to make purchases. This requires immediate resolution as it blocks core e-commerce functionality. Customer Support Chat Not Functioning (R5): Users cannot access live support via chat, impacting the customer service experience. This is critical to address, especially for resolving user issues in real-time. Conclusion & Recommendations The acceptance testing identified several significant gaps in functionality that prevent the web portal from being fully operational. The most urgent issues are related to core business functions, such as placing orders, booking test drives, and scheduling service appointments. Resolving these issues should be the top priority. Recommendations: Immediate bug fixes for the checkout and booking processes. Integration and testing of the payment gateway and service appointment features. Ensuring customer support chat and analytics tools are functioning correctly. After addressing these issues, a retest will be necessary to verify that the requirements are fully met. Next Steps: Development team to review and resolve the critical issues. Re-run acceptance testing after fixes are implemented.
Testing review summary:
Coverage | Completeness of tests | Accuracy of tests | Comments
This tests covers all divisions of the requirements for Skybot Web Portal. All main requirements are covered by tests, except security check in Web Hosting requirement division. Very important, that tests coverage is easy trackable by mentioning the requirements in every test. More tests can be added only with additional access to the portal's documentation, admin panels and involving dev team | This tests includes the requirement to trace the coverage, acceptance criteria, description of the feature under test, preconditions and test data, steps to execute, expected result description, test status, estimation of priority and comments. All parts of the test are descibed understandable, consistently and already performed. It is important to emphasize that different test approaches are used depending on the features under test: test cases, check lists, e2e user test scenarious. Tests are estimated by priority only by division of requirements, not each test separately. Also there is a recommendation for Steps To Execute to mention the tools and the procedure to provide described test steps. | 100% | The following points should be pointed out: 1. Documentation is performed in English, this is very professional 2. The test object is not ready, and the access to the dev team, portal's documentation, admin panel was absent for the testing team, that's why the completness of tests couldn't be 100% 3. in the overview the testing team mentioned, that "Several critical requirements were not fulfilled, which could severely impact the user experience and the commercial functionality of the portal" and mentioned all the issues in detail. It is also impacted the possibility of testing team to provide more complete testing. 4. Considering the mentioned above testing should be supplemented after the all needed access will be given and absent functionality will be ready.
Conclusion
The team of testers represented by Oleksandra Solodka did a great job using the requirement-based statements, prepared test data, correct test environment and consistent approach. This UAT, considering all the aspects of portal's readiness, the lack of documentation, access, communication with the devteam and other aspects is full-fledged and operative document, that could be used as a work instrument just now