## Test Structure
User Interface testing of the Skybot Mobile Application v. 1.0
Project: | Skybot Mobile Application
Iteration: | 1
Testing team: | Bohdan Prykhodchenko
Start date: | 2024-10-04
End date: | 2024-10-06
Description of the testing environment required to perform UI testing of the Skybot Mobile Application v. 1.0
Software | Hardware | Network | Requirements
Android 13 | Smartphone Xiaomi Mi 11 Lite 5G (CPU Qualcomm Snapdragon 780G, GPU Adreno 642, 6Gb RAM, 6.55" display with 2400x1080 (FullHD) resolution) | 4G mobile Kyivstar | Requirements analysis
Android 9 | Smartphone Xiaomi Mi A1 (CPU Qualcomm Snapdragon 625, GPU Adreno 506, 4Gb RAM, 5.5" display with 1920x1080 (FullHD) resolution) | wifi network up to 200 Mbit/s
Spaces: Follow Business
The structure of User Interface testing of the Skybot Mobile Application v. 1.0
Registration and Authorization
Verifies that the user can register in the SMA and authorize with registered data, all necessary input fields, promps, messages, confirmations and other functionality works as required
Product Viewing
Verifies that the user can view the products in the catalog with all details of the product, can use the product filter and search of the products as required
Product Details
Verifies that the user can view the product with all details such as name, image, characteristics, price, availability and description of the product, and can see the raiting and the reviews of the product
Adding to the Cart
Verifies that the user can add the product to the Cart and edit the Cart content: change the number of products, add or delete
Placing an Order
Verifies that the user can place an order, verify the Checkout and edit the purchase, add the delivery and contact info
Payment
Verifies that the user can pay an order by different options: by card, by payment system
Order Tracking
Verifies that the user can track an order by different options: receiving the order and payment confirmation, delivery status updatings
Reviews and Ratings
Verifies that the user can review the products and rate it by marks
UI Consistency
Verifies that the user interface and controls matches the web portal user interface
Summary
Summary of the UI testing

## Registration and Authorization
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
TC101 | High | Verify the presence and layout of the registration form UI elements. | 1. Navigate to the registration page. 2. Check if the registration form contains fields for: - Email address - Password - Confirm password - Register button 3. Verify the positioning and alignment of the form fields and button. | The form fields should be clearly labeled and aligned. The "Register" button should be placed prominently below the form fields. | Pass
TC102 | Medium | Check the email input field UI, including its validation. | 1. Navigate to the registration page. 2. Try entering an invalid email format 3. Check if an error message is displayed when the email format is invalid. 4. Enter a valid email format. 5. Verify that no error message is displayed for valid email input. | An error message should appear for invalid email formats, and the input field should have proper styling (e.g., red border) when the email format is incorrect. No error should appear for valid input. | Pass
TC103 | Low | Ensure that the password input field is secure and the visibility toggle works. | 1. Enter a password into the password field. 2. Check if the password is displayed as hidden (dots/asterisks). 3. Use the "eye" icon (or visibility toggle) to show the password. 4. Toggle it back to hide the password. | The password should be hidden by default and displayed in plain text when the visibility toggle is used. The toggle should function properly. | Pass
TC104 | Low | Check the appearance and behavior of error messages for required fields. | 1. Navigate to the registration page. 2. Attempt to submit the registration form without filling in any fields. 3. Observe the error messages for missing fields (email, password). | Error messages should appear below or next to each required field, indicating that the field must be filled (e.g., "Email is required," "Password is required"). | Pass
TC105 | High | Ensure that a successful registration is confirmed through the UI. | 1. Fill in the registration form with valid email and password. 2. Submit the form. 3. Check if a success message or confirmation page appears | A confirmation message (e.g., "Registration successful") should appear, or the user should be redirected to a welcome page or login page after successful registration. | Pass
TC106 | High | Verify the presence and layout of the login form UI elements. | 1. Navigate to the login page. 2. Check if the login form contains fields for: - Email address - Password - Login button - "Forgot Password" link 3. Verify the positioning and alignment of the form fields and button. | The form fields and "Login" button should be well-positioned and clearly visible. The "Forgot Password" link should be placed near the password field. | Pass
TC107 | Low | Validate the email field on the login page for correct input. | 1. Navigate to the login page. 2. Enter an invalid email format 3. Check if an error message is displayed when the email format is invalid. | The email field should display an error for invalid formats, and the error message should be clearly visible. | Pass
TC108 | Low | Check the error message appearance when incorrect login credentials are entered. | 1. Enter a valid email but an incorrect password. 2. Submit the login form. 3. Observe the appearance of an error message. | An error message like "Incorrect email or password" should be displayed in a noticeable way, guiding the user to try again. | Pass
TC109 | High | Ensure the "Forgot Password" link is present and functional. | 1. Locate the "Forgot Password" link on the login page. 2. Click on the link. 3. Verify that it redirects to the password recovery page. | The link should navigate the user to the password recovery page, which contains fields for email input to reset the password. | Pass
TC110 | High | Verify that the user is logged in successfully and redirected after login. | 1. Enter valid email and password credentials. 2. Submit the login form. 3. Check if the user is redirected to the homepage or dashboard after successful login. | Upon successful login, the user should be redirected to a designated page (e.g., dashboard or homepage) without any errors. | Pass
TC111 | Medium | Verify the presence and layout of the Log Out form UI elements. | 1. Navigate to the My Profile page. 2. Check if the Log Out button is present 3. Verify the positioning and alignment of the button is clearly visiable. | The form fields and "Log Out" button should be well-positioned and clearly visible. | Pass
TC112 | Medium | Verify that the user can Log Out | 1. Navigate to the My Profile page. 2. Use the Log Out button 3. Proceed to Log Out | User should be able to Log Out from the App | Pass

## Product Viewing
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
TC201 | High | Verify that the catalog displays the correct elements for each product: name, image, description, price, and availability. | 1. Navigate to the product catalog page. 2. Verify product name, image, description, price, and availability. 3. Check alignment and layout. | Products should display all info with a uniform layout. | Fail | In the Shop page the availability and the description of the products are absent
TC202 | Medium | Verify that product images are displayed correctly as preview and in zoom mode | 1. Navigate to the product catalog page. 2. Check image preview. 3. Zoom the image. | Images maintain quality and displayed correctly as preview and in zoom mode. | Pass
TC203 | Medium | Ensure that product filter options (categories, brands, price range) are visible and accessible. | 1. Navigate to the catalog page. 2. Locate filter panel (categories, brands, price range). 3. Verify accessibility. | Filter options should be accessible and well-organized. | Fail | In the Shop page the Filter of the products is absent
TC204 | Medium | Check the UI and functionality of filtering products by category. | 1. Open category filter. 2. Select a category. 3. Verify filtered product display. | Only products from the selected category should be shown. | Fail | In the Shop page the Filter of the products is absent
TC205 | Medium | Verify the UI and functionality of filtering products by brand. | 1. Open brand filter. 2. Select a brand. 3. Verify filtered product display. | Only products from the selected brand should be shown. | Fail | In the Shop page the Filter of the products is absent
TC206 | Medium | Verify the UI and functionality of filtering products by price range. | 1. Open price filter. 2. Select price range. 3. Verify filtered product display. | Products within the selected price range should be shown. | Fail | In the Shop page the Filter of the products is absent
TC207 | Medium | Test how the UI handles multiple filters applied simultaneously. | 1. Apply category, brand, and price filters. 2. Verify filtered results. | All applied filters should display matching products. | Fail | In the Shop page the Filter of the products is absent
TC208 | High | Verify that the search bar is visible and properly placed on the page. | 1. Navigate to product catalog. 2. Check search bar placement. 3. Verify no UI overlap. | Search bar should be accessible and well-placed. | Pass
TC209 | Medium | Test the UI and functionality of searching for products by name. | 1. Enter product name in search bar. 2. Submit search. 3. Verify results. | Products matching the name should be displayed. | Pass
TC210 | Medium | Test the UI and functionality of searching for products using keywords. | 1. Enter keyword in search bar. 2. Submit search. 3. Verify results. | Products matching the keyword should be displayed. | Pass
TC211 | Low | Verify how the UI handles search queries that return no results. | 1. Enter invalid search term. 2. Submit search. 3. Verify no results message. | No results message should be shown for invalid queries. | Pass
TC212 | Medium | Ensure that the search results display correctly across different screen sizes. | 1. Perform a search. 2. Resize window or use mobile device. 3. Verify responsive layout. | Search results should be responsive and adjust properly. | Pass
TC213 | High | Verify gesture controls so that user can swipe, pinch and tap to use the app | 1. Open the App 2. Verify if the user can swipe to navigate through products in the catalog. 3. Ensure that users can tap on the image and pinch to zoom in and out of product images. 4. Check that users can tap to select a product from the product list. 5. Test that users can swipe to remove a product from the shopping cart. | User can swipe, pinch and tap to use the app | Pass

## Product Details
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
TC301 | High | Verify that the product details page displays all necessary elements: specifications, description, rating, reviews, and images. | 1. Navigate to the product details page. 2. Check for the presence of specifications, description, rating, reviews, and images. 3. Ensure correct alignment and layout. | The page should display all product details in a well-organized manner, without misalignment or missing information. | Fail | There are no specification, rating, reviews, only the text description (not all products) and images
TC302 | Medium | Ensure that the product description is visible, properly formatted, and located in the correct section. | 1. Navigate to the product details page. 2. Locate the product description. 3. Verify that the description is formatted properly. | The product description should be clearly visible, properly formatted, and located in its designated section. | Fail | Description_without_formatting
TC303 | Medium | Verify that product ratings and user reviews are displayed correctly, along with their respective scores. | 1. Check the product rating and user reviews section. 2. Verify that ratings are visible and reviews are displayed in the correct format. | Ratings and reviews should be displayed with correct scores and formatting, making it easy for users to read. | Fail | There are no rating and reviews
TC304 | Medium | Ensure that all product images are clearly displayed and adjust well to different screen sizes. | 1. Navigate to the product details page. 2. Check the product images. 3. Verify image quality and responsiveness to screen size. | Product images should maintain good quality and adjust responsively on different screen sizes. | Pass
TC305 | Medium | Check that the product specifications are presented in a readable format and are easy to locate. | 1. Navigate to the product details page. 2. Locate the product specifications section. 3. Verify that specifications are clear and well-structured. | Product specifications should be easy to read and formatted for clarity, located in a visible section. | Fail | There are no specifications

## Adding to the Cart
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
TC401 | High | Verify that the 'Add to Cart' button is functional and properly displayed on the product details page. | 1. Navigate to the product details page. 2. Locate the 'Add to Cart' button. 3. Click the button and verify product is added. | Add to Cart' button should be functional and visibly placed on the product page. | Pass
TC402 | High | Ensure that the cart icon updates (e.g., showing the number of items) after adding a product. | 1. Add a product to the cart. 2. Check if the cart icon updates to show the number of items added. | The cart icon should display the correct number of items after a product is added. | Pass
TC403 | High | Test that users can modify the product quantity in the cart and the UI updates accordingly. | 1. Add a product to the cart. 2. Go to the cart page. 3. Increase or decrease the quantity of the product and verify the change. | The cart should reflect the updated quantity for the selected product. | Pass
TC404 | High | Verify that users can remove a product from the cart and the cart updates correctly. | 1. Add a product to the cart. 2. Navigate to the cart. 3. Remove the product and check if the cart updates. | The cart should no longer show the removed product and should update accordingly. | Pass
TC405 | High | Check that the cart updates the total quantity and price when products are added or removed. | 1. Add or remove products in the cart. 2. Verify that the total quantity and price update correctly on the cart page. | The cart total (quantity and price) should update immediately when products are added or removed. | Pass

## Placing an Order
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
TC501 | High | Verify that users can review the contents of their cart before proceeding to checkout. | 1. Add items to the cart. 2. Navigate to the cart page. 3. Review the list of items before checkout. | Users should see an accurate list of products in their cart before placing an order. | Skipped | Checkout is not ready
TC502 | High | Ensure that users can modify the quantity or remove items from the cart before placing an order. | 1. Add items to the cart. 2. Go to the cart page. 3. Modify the quantity or remove an item. 4. Verify that changes are saved. | Users should be able to change quantities or remove items, with changes saved correctly. | Skipped
TC503 | High | Check that users can proceed to the checkout page after reviewing their cart. | 1. Add items to the cart. 2. Review the cart. 3. Click 'Proceed to Checkout' and verify navigation to the checkout page. | Users should be able to proceed to the checkout after reviewing and modifying their cart. | Skipped
TC504 | High | Test that users can enter and save a valid shipping address before placing the order. | 1. On the checkout page, locate the shipping address form. 2. Enter a valid address. 3. Verify that the address is saved and shown correctly. | Shipping address should be saved and displayed correctly on the checkout page. | Skipped
TC505 | High | Verify that users can enter and save valid contact information (phone, email) during checkout | 1. On the checkout page, locate the contact information form. 2. Enter valid contact details (phone, email). 3. Verify that the details are saved. | Contact information should be saved and shown correctly on the checkout page. | Skipped

## Payment
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
TC601 | High | Verify that users can select different payment methods (credit card, payment systems) during checkout. | 1. Navigate to the checkout page. 2. Review available payment methods. 3. Select a preferred payment method. | Users should be able to select their preferred payment method during the checkout process. | Skipped | Checkout is not ready
TC602 | High | Ensure that the credit card payment form is displayed and functioning correctly. | 1. On the payment page, select 'Credit Card' as the payment method. 2. Enter valid credit card information. 3. Complete the transaction. | Credit card payment form should function correctly, and users should be able to complete payments successfully. | Skipped
TC603 | Medium | Check that users can successfully complete a payment using a third-party payment gateway (e.g., PayPal, GooglePay, ApplePay). | 1. On the payment page, select a third-party payment gateway (e.g., PayPal). 2. Complete the transaction via the external gateway. | Users should be redirected to the payment gateway and complete the transaction without errors. | Skipped
TC604 | Medium | Test that users receive a payment confirmation after successfully completing a payment. | 1. Complete the payment process. 2. Verify that a confirmation message is displayed and payment details are provided. | After completing the payment, users should receive a confirmation message with order and payment details. | Skipped

## Order Tracking
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
TC701 | High | Verify that users receive an order confirmation status after placing an order. | 1. Place an order. 2. Verify that the system displays an order confirmation notification. | Users should receive a confirmation notification or email after placing an order. | Skipped | Checkout is not ready
TC702 | High | Ensure that users receive a payment confirmation update after the payment is processed. | 1. Complete the payment. 2. Verify that a payment confirmation is displayed or sent to the user. | Users should be notified when payment is successfully processed. | Skipped
TC703 | Medium | Check that users are notified of the shipment status when the order is shipped. | 1. Ship the order from the admin panel. 2. Check that the user is notified of the shipment status. | Users should be notified when their order is shipped. | Skipped
TC704 | Medium | Test that users receive updates when the order is out for delivery and when it is delivered. | 1. Update the order status to 'out for delivery' and then 'delivered'. 2. Verify that the user receives updates for both statuses. | Users should receive updates when the order is out for delivery and when it is delivered. | Skipped

## Reviews and Ratings
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
TC801 | Medium | Verify that users can leave a review for a product after purchase. | 1. Navigate to the product page. 2. Scroll to the reviews section. 3. Enter a review and submit it. | Users should be able to submit a review for a product. | Fail | Review and rating options are absent
TC802 | Medium | Ensure that users can rate a product on a scale (e.g., 1-5 stars) after purchase. | 1. Navigate to the product page. 2. Select a rating (e.g., 1-5 stars). 3. Submit the rating. | Users should be able to rate the product on a scale (e.g., 1-5 stars). | Fail
TC803 | Low | Check that the system confirms the submission of the review and rating. | 1. Submit a review and rating. 2. Verify that a confirmation message or notification is displayed. | After submission, the system should confirm that the review and rating were successfully recorded. | Fail

## UI Consistency
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
TC901 | Medium | Verify that the user interface of the mobile app is visually consistent with the web portal. | 1. Open the mobile app and the web portal. 2. Compare the user interface design between the two platforms. | The mobile app UI should be visually consistent with the web portal for brand recognition. | Fail | The slider in the SMA is absent, the number of pages and the content doesn't match
TC902 | Medium | Ensure that the brand design (colors, logos, fonts) is identical between the mobile app and web portal. | 1. Open both the mobile app and the web portal. 2. Verify that the color scheme, fonts, and logos are consistent between the two. | The visual elements (color scheme, fonts, logos) should be identical between the mobile app and web portal. | Fail | The content doesn't match
TC903 | Medium | Check that all control elements (buttons, menus, navigation) in the mobile app match the web portal. | 1. Navigate through the mobile app and the web portal. 2. Compare the placement, size, and style of control elements. | Control elements (buttons, menus) should be the same on both platforms in terms of design and layout. | Pass | Both are black text on the white background
TC904 | Medium | Ensure that the functionality of control elements in the mobile app behaves identically to the web portal (e.g., buttons, navigation). | 1. Use control elements (e.g., buttons, menus) in both the mobile app and the web portal. 2. Verify that the controls behave the same way on both platforms. | Controls in the mobile app should function the same way as those on the web portal. | Fail | SMA has only 5 buttons in the header: Shop, Home, Schedule, Services and Videos. The Portal has more: 10 buttons and they doesnt match
TC905 | Medium | Ensure that the design of the main page and it's functional elements is clear and visiable for the user | 1. Open the mobile app. 2. Check if the buttons in the header are visiable and understandable for the user. 3. Check if the buttons in the bottom are visiable and understandable for the user. | The buttons in the header and in the bottom are visiable and understandable for the user. | Fail | The buttons of the pages in the header are not very visiable, small type, transparent background.
TC906 | Medium | Ensure that the user interface of the mobile app is comprehensive and contains all required sections of functionality | 1. Open the mobile app. 2. Check if the main pages and sections of functionality of the SMA meets the web portal main pages and sections of functionality | The user interface of the mobile app is comprehensive and contains all required sections of functionality | Fail | The number of functional sections is less than in the web portal, the SMA is not comprehensive. FAQ, Support, About, Careers, Members and Store Policies sections are absent. The requirements should be supplemented to clarify the correspondence between the functionality of the web portal and the mobile application. Home page in SMA is not ready

## Summary
Test division | Test results | Issues
Registration and Authorization | 100% | Everything works well
Product Viewing | 45% | The availability and the description of the products are absent, the Filter is absent
Product Details | 20% | There are no specification, rating, reviews, only the text description (not all products) and images. Also the content is not formatted
Adding to the Cart | 100% | Everything works well. Promocode test could be added if required and if the test promocode will be available
Placing an Order | Skipped | Checkout is not ready
Payment | Skipped | Checkout is not ready
Order Tracking | Skipped | Checkout is not ready
Reviews and Ratings | 0% | Review and rating options are absent
UI Consistency | 15% | The UI is not consistent and doesn't match the functionality, requirements should be supplemented to clarify the correspondence between the functionality of the web portal and the mobile application
Conclusion: | The SMA has a limited readyness, the clue business functions (Checkout, Payment, Order) are absent, the UI is not consistens with the portal. The content of products needed to be to expanded by formatting, reviews, ratings, specifications and filter option.