## Test environment
Acceptance testing for Skybot portal v 3.0
Project name: |  | Skybot portal
Testing start date: |  | 2024-09-06
Testing end date: |  | 2024-09-08
Performed by: |  | Bohdan Prykhodchenko
Iteration: |  | 1
Description of the testing environment required to perform Acceptance testing of the Skybot portal v 3.0
Software | OS | Browser | Device | Hardware | Network connection | Test Data | Requirements | Access | Involved staff
| Windows 11 Pro 23H2 64bit | Chrome128.0.6613.120 | Laptop Dell Latitude 7490 | CPU Intel i5-8350U, GPU Intel UHD Graphics 620, 16Gb RAM, SSD hard drive, mouse, 27" display with 2560 x 1440 (2K) resolution | fixed lan-wifi network up to 200 Mbit/s | https://prometheusqastage3.wixsite.com/skybot | Оновлені вимоги до порталу | Hosting admin panel | Testing team
| Android 13 | Firefox 129.0.2 | Smartphone Xiaomi Mi 11 Lite 5G | CPU Qualcomm Snapdragon 780G, GPU Adreno 642, 6Gb RAM, 6.55" display with 2400x1080 (FullHD) resolution | 4G mobile network Kyivstar | Login |  | Portal admin panel | Stakeholders
| Android 9 | Firefox 129.0.2 | Smartphone Xiaomi Mi A1 | CPU Qualcomm Snapdragon 625, GPU Adreno 506, 4Gb RAM, 5.5" display with 1920x1080 (FullHD) resolution |  | 13102020kh@ukr.net |  | Domain admin panel | Design team representative
[6 empty] | Password |  | Portal's email service | Developer team representative
[6 empty] | Ta12345ra |  | Portal's database | DevOps representative
[8 empty] | Portal output data | Project manager
The structure of Acceptance testing for Skybot portal v 3.0
Web hosting |  | Verifies that the web hosting is fast, stable and secure as required
Mobile version |  | Verifies that the mobile version is capable of working on mobile devices and supports all the necessary functionality
Design |  | Verifies that the Design is convenient and intuitive with the ability to update
Frontend |  | Verifies that the Frontend side of the portal is stable and ensures smooth operation of the portal
Backend |  | Verifies that the Backend is reliable, ensures continuous operation of the portal and provides data processing and interaction with the frontend
Purchase |  | Verifies that the user can make a purchase
Security |  | Verifies that the portal provides a high level of security for users during registration, authorization and making payments
Product page |  | Verifies that the product pages contains information about each model of electric transport with a detailed description
Test-drive |  | Verifies that the portal provide users with the opportunity to easily and conveniently sign up for a test drive of the selected model of electric transport through the web portal
Service booking |  | Verifies that the portal provides users with a convenient and quick appointment for service or repair at a service center after purchasing a vehicle on the web portal
Reviews |  | Verifies that the user can leave and view the reviews of the products
Recommendations |  | Verifies that the user can receive a personalized recommendations for electric transport products
Videos |  | Verifies that the user can view video reviews of products (models of electric vehicles), integrated videos from popular video hosting platforms
Analytics |  | Verifies that the portal provides necessary infrastructure and integrations to use analytics tools on the portal to collect, analyze and use data to improve operations and user experience
Summary |  | Summary of the acceptance test

## Web hosting
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
101 | Medium | Measure the page load time to ensure it’s less than 2 seconds | 1. Create and pull a request Get in Postman with https://prometheusqastage3.wixsite.com/skybot adress 2. Check the load time | less than 2 seconds | Pass
102 | Low | Verify Login Response Time | 1. Create and pull a request Get in Postman with https://prometheusqastage3.wixsite.com/skybot 2. Use an authorisation in the request, put the valid login and password 2. Commit the request and check the load time | less than 2 seconds | Pass
103 | Low | Verify file upload time | 1. Open the https://prometheusqastage3.wixsite.com/skybot 2. Log in with a valid data 3. Go to the product page 4. Make the review and upload a 5mb image 5. Measure the time of uploading using the browser Dev Tools | less than 5 seconds | Pass
104 | Low | Verify page response under load | 1. Simulate a high number of simultaneous requests to the home page 2. Measure the average response time. | The average response time should be less than 3 seconds even under load | Pass
105 | Medium | Check if a server-side caching is implemented and active | 1. Open https://seositecheckup.com/seo-audit/page-cache-test-server-side-caching/ 2. Put the adress https://prometheusqastage3.wixsite.com/skybot 3. Choose the server-side caching test 4. Get the answer | server-side caching is implemented and active | Pass
106 | Medium | Check if a CDN is implemented and active for serving static content using Postman | 1. Create and pull a request Get in Postman with https://prometheusqastage3.wixsite.com/skybot adress 2. Check the CDN in the Body of the page | CDN is used | Pass
107 | Medium | Check if a html-cacheable is implemented and active with the Postman tool | 1. Create and pull a request Get in Postman with https://prometheusqastage3.wixsite.com/skybot adress 2. Check the Html-cacheable parametr is true | The Html-cacheable parametr is true | Pass
108 | Medium | Ensure asynchronous loading of resources to prioritize main page content | 1. Open the portal https://prometheusqastage3.wixsite.com/skybot adress 2. Check the loading progress by browser Dev Tools | Asynchronous loading is present | Pass
109 | Medium | Ensure Lazy Loading technology is used | 1. Open the portal https://prometheusqastage3.wixsite.com/skybot adress 2. Check the loading progress by browser Dev Tools | Lazy Loading technology is present | Pass
110 | Medium | Check if a server-side caching is implemented and active using Seositecheckup tool | 1. Open https://seositecheckup.com/seo-audit/page-cache-test-server-side-caching/ 2. Put the adress https://prometheusqastage3.wixsite.com/skybot 3. Choose the server-side caching test 4. Get the answer | Server-side caching is implemented and active | Pass
111 | High | Vefiry if the servers are deployed on the SSD hard drives | 1. Ask the hosting provider if the servers are deployed on the SSD hard drives | Servers are deployed on the SSD hard drives | Blocked | There is no access to the hosting admin panel
112 | High | Verify if the web hosting uptime is not less than 99,9% | 1. Ask the hosting provider if the uptime not less than 99,9% is available | The uptime not less than 99,9% is available | Pass
113 | Medium | Verify if the provider branching servers in different locations to avoid local risks | 1. Ask the hosting provider if branching servers in different locations is available | Branching servers in different locations is available | Blocked | There is no access to the hosting admin panel
114 | High | Verify if the provider backing up the server's data automatically | 1. Ask the hosting provider if backing up the server's data automatically is available | Backing up the server's data automatically is available | Blocked | There is no access to the hosting admin panel
115 | Medium | Verify if the provider has a scalability option to expand the server's performance | 1. Ask the hosting provider if a scalability option to expand the server's performance is available | Scalability option to expand the server's performance is available | Blocked | There is no access to the hosting admin panel
116 | High | Check if SSL is used on the web-site | 1. Create and pull a request Get in Postman with https://prometheusqastage3.wixsite.com/skybot adress 2. Turn on the SSL certificate verification | SSL certification is present | Pass
117 | Medium | Verify if XSS and CSRF defence is used on the portal | 1. Visit https://pentest-tools.com/website-vulnerability-scanning/xss-scanner-online and enter https://prometheusqastage3.wixsite.com/skybot adress 2. Check the XSS 3. Check the CSRF | the XSS and CSRF defence is present | Pass
118 | Medium | Verify that the web portal has protection mechanisms against Distributed Denial of Service (DDoS) attacks | 1. CHeck if DDoS protection is enable in the hosting admin panel 2. Simulate a DDoS attack using a testing tool or service. 3. Monitor the portal’s response to the simulated attack. | The web portal should remain responsive, with minimal impact on performance, indicating effective DDoS protection | Pass
119 | Medium | Ensure that multi-factor authentication is enabled for administrative access to the web portal and servers | 1. Attempt to log in to the administrative portal with a valid username and password. 2. Verify if an additional authentication step (e.g., SMS code, app-based token) is required | Administrative access should require multi-factor authentication, adding an extra layer of security | Blocked | There is no access to the hosting admin panel
120 | Medium | Ensure that access to administrative areas is restricted based on IP addresses | 1. Attempt to access the administrative portal from an unauthorized IP address. 2. Attempt to access the administrative portal from an authorized IP address. | Access to administrative areas is based only on authorized IP address | Blocked | There is no access to the hosting admin panel
121 | High | Verify if the Web application firewall is used on the portal hosting | 1. Ask the hosting provider if the Web application firewall is used on the portal hosting | Web application firewall is used on the portal hosting | Blocked | There is no access to the hosting admin panel
122 | High | Verify if the tech support is available 24/7 on the portal hosting | 1. Ask the hosting provider if the tech support is available 24/7 on the portal hosting | Tech support is available 24/7 on the portal hosting | Blocked | There is no access to the hosting admin panel

## Mobile version
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
201 | Medium | Measure the page load time on mobile device using mobile data 4G with the Rest Client tool to ensure it’s less than 3 seconds | 1. Create and pull a request Get in Rest Client on the mobile device with https://prometheusqastage3.wixsite.com/skybot adress, using 4g mobile data connection 2. Check the load time | less than 3 seconds | Pass
202 | Medium | Check if a html-cacheable is implemented and active in mobile version with the Rest Client tool | 1. Create and pull a request Get in Rest Client on the mobile device with https://prometheusqastage3.wixsite.com/skybot adress, using 4g mobile data connection 2. Check the Html-cacheable parametr is true | The Html-cacheable parametr is true | Pass
203 | Medium | Ensure asynchronous loading of resources to prioritize main page content in mobile version | 1. Open the site under Android smartphone 2. Check the asynchronous loading in loading progress by mobile device browser | Asynchronous loading is present | Pass
204 | Medium | Ensure Lazy Loading technology is used in mobile version | 1. Open the site under Android smartphone 2. Check the lazy loading in loading progress by mobile device browser | Lazy Loading technology is present | Pass
205 | High | Check if the portal is readable with all neccessary functionality and proper visual displaying using horizontal and vertical screen and zoom in the mobile version by using Android with Chrome browser | 1. Open the site under Android smartphone using Chrome 2. Observe the site in horizontal and vertical orientation using zoom, scrolling and using zoomed buttons and forms 3. Check the site view, corrrect design and scale showing | Site is opened, all functionality works even zoomed, the visual display is correct | Fail | In horizontal screen orientation the portal is hardly readable, products are too big and the chat button overlaps the menu button so the user couldn't navigate easily
206 | High | Check if the portal is readable with all neccessary functionality and proper visual displaying using horizontal and vertical screen and zoom in the mobile version by using Android with Firefox browser | 1. Open the site under Android smartphone using Firefox 2. Observe the site in horizontal and vertical orientation using zoom, scrolling and using zoomed buttons and forms 3. Check the site view, corrrect design and scale showing | Site is opened, all functionality works even zoomed, the visual display is correct | Fail | In horizontal screen orientation the portal is hardly readable, products are too big and the chat button overlaps the menu button so the user couldn't navigate easily
207 | High | Check if the portal is readable with all neccessary functionality and proper visual displaying using horizontal and vertical screen and zoom in the mobile version by using Iphone with Safari browser | 1. Open the site under Iphone smartphone using Safari 2. Observe the site in horizontal and vertical orientation using zoom, scrolling and using zoomed buttons and forms 3. Check the site view, corrrect design and scale showing | Site is opened, all functionality works even zoomed, the visual display is correct | Fail | In horizontal screen orientation the portal is hardly readable, products are too big and the chat button overlaps the menu button so the user couldn't navigate easily
208 | High | Confirm that the portal adjusts automatically to different screen sizes and orientations of mobile devices | 1. Open the portal using different supported mobile devices 2. Check that the portal adjusts automatically to different screen sizes and orientations of mobile devices properly | The portal is showed properly on different screen sizes and orientations of mobile devices | Fail | In horizontal screen orientation the portal is hardly readable, products are too big and the chat button overlaps the menu button so the user couldn't navigate easily
209 | Medium | Confirl that the portal is using the media queries to adopt styles for different parametrs of mobile devices | 1. Open https://seositecheckup.com/seo-audit/page-cache-test-server-side-caching/ 2. Put the adress https://prometheusqastage3.wixsite.com/skybot 3. Choose the media-query test 4. Get the answer | Media queries are used | Pass
210 | Medium | Confirl that the portal is using the flexible mesh to organize elements of the interface | 1. Open the site under Android smartphone 2. Check the the flexible mesh is used to organize elements of the interface to provide portal's usability on different screen sizes | Flexible mesh is used to organize elements of the interface to provide portal's usability on different screen sizes | Fail | Elements of the interface are not adopting correctly on different screen sizes
211 | High | Confirm that the portal is optimized up to the modern technologies for the required performance | 1. Open https://pagespeed.web.dev/analysis 2. Put the adress https://prometheusqastage3.wixsite.com/skybot 3. Analyse 4. Get the report and check if the portal is optimized by its resources and images | The portal is optimized by its resources and images | Fail | The portal has a list of issues and recommendations to improve using different technologies and approaches
212 | High | Verify User Registration on mobile device | 1. Open the portal https://prometheusqastage3.wixsite.com/skybot 2. Go to the Sign Up page 3. Enter valid password and login (email) and proceed 4. Confirm the registration by email 5. Log in on the portal with registered pass and login | The user should be able to Sign Up successfully and be able to Log In successfully | Pass
213 | High | Verify User Login on mobile device | 1. Open the portal https://prometheusqastage3.wixsite.com/skybot 2. Go to the login page 3. Enter valid password and login and proceed | The user should be able to log in successfully and be redirected to their dashboard | Pass
214 | Medium | Verify Logout Functionality on mobile device | 1. Login to the web portal https://prometheusqastage3.wixsite.com/skybot 2. Click on the "Logout" button. | User should be logged out and redirected to the login page | Pass
215 | High | Verify Navigation Menu on mobile device | 1. Open the portal https://prometheusqastage3.wixsite.com/skybot 2. Click on the navigation menu icon | The navigation menu should open smoothly, displaying all menu items correctly | Pass
216 | Medium | Verify if elements of the interface are big enough to use on the little screen | 1. Open the portal https://prometheusqastage3.wixsite.com/skybot using the 5,5" smartphone (Android 9, Xiaomi Mi A1, Firefox) 2. Check elements of the interface if they are big enough to use comfortable | The interface are big enough to use on the little screen | Pass

## Design
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
301 | High | Verify the structure of portal is logic and understandable for user | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Check the home page of portal according to the business logic and user stories: the content, pictures, functional elements are in the direct order and placed correctly, it needs minimum steps to use the main functions and all needed functionality is visible and named understandable 3. Check all main pages of portal according to the business logic and user stories: the content, pictures, functional elements are in the direct order and placed correctly, it needs minimum steps to use the main functions and all needed functionality is visible and named understandable | Portal is structured logically, it is possible to reach the neccessery pages, forms or functions with minimal quantity of steps and without a special knowledge about the portal and its structure | Fail | 1. Some functions are not ready, such as checkout, payments, or even page layout (issues described in scalability, navigation testing) etc 2. Main page named "Main" but before it was "Home", it should be ambiguity how to name it corrrect 3.There are unneccessary elements such as the content from the About Us page such as map, Support form from Support page. 4. Scrolling the page from the bottom up to the top works bad, user can see only the background but not the content 5. Groups of members placed in the Main page is not required, requirements should be developed 6. Video reviews page is not required, requirements should be developed. 7. Booking the service and renting the vehicle mixed in one page and it is confusing
302 | Medium | Verify the structure of portal has clearly defined sections and subdivisions | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Check if portal is devided by the sections according to the business logic and user stories: all sections are presented in the direct order and placed correctly with the proper content, pictures, functional elements 3. Check if portal is devided by the subdivisions according to the business logic and user stories: all subdivisions are presented in the direct order and placed correctly with the proper content, pictures, functional elements | Portal has clearly defined sections and subdivisions | Fail | Portal has clearly defined sections and subdivisions, but some functions ot buttons are not required, such as: Video reviews page and button, Careers page and button. And instead of 2 functions (to rent a vehicle and to book a service) there is only 1 mixed: Our services
303 | Medium | Verify the path of all main user's activities is available with minimum clicks | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Check the availability of user's activities: to register, to place an order, to browse different pages, to fill the forms, to scroll the content 3. Check the steps to reach the neccessery user's activity for it's logic and necessity | The path of all main user's activities is available with minimum clicks, easy to find and to use | Fail | Many of user's activities are not ready or impossible to use, such as to proceed in the cart, to have recommendations or to book a service. Recommendation to proceed this test when general user's functionality will be ready
304 | Medium | Verify the unification of the portal's style for all design elements (font, colours, buttons) | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Check the fonts on the portal pages if they are unified 3. Check the colours on the portal pages if they are unified 4. Check the buttons on the portal pages if they are unified | Portal's style is unified for all design elements | Fail | Portal's style is mostly unified for all design elements. But: 1. Stakeholder doesn't like the Cart icon 2. Buttons of main pages in the header are too small in desktop version 3. The Slider is too big and overlaps the content when scrolling 4. Picture of the standard bicycle on the Careers page doesn't meet the purpose of the portal (non-electric byke)
305 | Medium | Verify using visual hierarchy: different types of fonts and colour contrasts for accenting the important elements and using the white colour to devide the content | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Check the fonts and colour contrast of the important elements of the portal 3. Check the white colour is deviding the content | Different types of fonts and colour contrasts for accenting the important elements are used and the white colour devided the content | Pass
306 | Medium | Verify if high contrast of text and background is used to make the site readable | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Check if high contrast of text and background is used to make the site readable | High contrast of text and background is used | Pass
307 | Low | Verify if the alternative text for pictures is present so that visually impaired users could have the access to the information | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Check if the alternative text for pictures is present so that visually impaired users could have the access to the information | The alternative text for pictures is present | Fail | The alternative text for pictures is absent
308 | Low | Verify the site's navigation without a mouse is possible | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Browse the site without using the mouse to confirm the site's navigation without a mouse is possible | The site's navigation without a mouse is possible | Pass
309 | Low | Verify if WCAG recommendations and ARIA attributes are implemented | 1. Visit the test tool https://wave.webaim.org , put the porta's adress https://prometheusqastage3.wixsite.com/skybot 2. Verify compliance with WCAG and ARIA according to the WCAG recommendations and ARIA attributes | WCAG recommendations and ARIA attributes are implemented | Fail | WCAG recommendations and ARIA attributes are not implemented
310 | Medium | Check if the portal is readable with all neccessary functionality and proper visual displaying using different screen resolutions and scales in the desktop version, flexible images and mockups are used to adjust the size up to the different screen size | 1. Open the site under Windows OS 10/11, using Chrome, Firefox, Edge and Safari (native) Open the site under Mac OS 14/15 using Safari Open the site under Linux 24/25 Chrome, Firefox, Edge Open the site using different screen resolutions (1920×1080, 1366×768, 1280×1024, 1440×900, 1600×900, 1680×1050, 1280×800, 1024×768) 2. Try different scale displaying (90%, 75%, 50%, 150%, 300% etc) 3. Check the site elements functionality 4. Check the site view, corrrect design and scale showing | Site is opened, all functionality works, the visual display is correct | Fail | The visual display in PC version is incorrect. The scale and proportions of the site displaying should be corrected, because the header is too small, the slider, language switcher and other elements doesn't fit the screen, user should scroll even horizontal to see them. The slider scrolls not correct, is cut on the top of scrolls to fast, scaling doesn`t help to view the whole page at the screen etc.
311 | Low | Verify if the pictures on portal are corresponding to it's purpose | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Check if the pictures on the home page and all other available pages are corresponding to portal's purpose | The pictures on portal are corresponding to it's purpose | Fail | Picture of the standard bicycle on the Careers page doesn't meet the purpose of the portal (non-electric byke)
312 | Medium | Verify the Usability testing with users was provided successfully | 1. Check the report of Usability testing with users 2. Check if the issues and propositions mentioned in the report are fixed or provided | The Usability testing with users was successfull | Fail | Usability testing with users was not provided
313 | Low | Check the feedback about design from users | 1. Check the feedback from the portal users | The feedback about design from users is realized and works correctly, feedbacks are collecting | Fail | The feedback from users is not realized yet
314 | Medium | Check if the modular design used by the component approach and interface elements can be replaced without affecting other parts of the portal | 1. Aks the design team to show the design output to check if it is based on the modules 2. Check the interface elements can be replaces without affecting other parts of the portal | The modular design is provided in portal successfully | Blocked | The design team is not involved to the testing, there is no data and access to test this item
315 | Medium | Check if it is it possible to change CSS styles easily to update portal`s appearance | 1. Aks the design team if it is it possible to change CSS styles easily to update portal`s appearance 2. Change CSS styles to check the procedure is easy and works correctly | It is possible to change CSS styles easily to update portal`s appearance | Blocked | The design team is not involved to the testing, there is no data and access to test this item
316 | Low | Check if it is possible to change the design themes by admin panel | 1. Access the admin panel 2. Check the design themes change is available | The design themes change is available | Blocked | There is no access to the admin panel
317 | Low | Verify the user can customize the interface | 1. Access the user's My Account 2. Check the option to customize the interface | The user can customize the interface | Fail | There is no such option to customize the interface for user
318 | Medium | Check if it is possible to integrate new functions and technologies without significant changes in the existent design | 1. Develop the requirements for this functionality 2. Develop the functionality according the requirements 3. Test the functionality according the requirements | The admin can integrate new functions and technologies without significant changes in the existent design | Fail | The requirement is incomplete and ambiguous: there are too many different functions and technologies now and could be even more in the nearest future. It is needed to specificate requirements first, what exact functions and technoligies are needed.
319 | Medium | Check if it is possible to add new plugins and widgets without significant changes in the existent design | 1. Develop the requirements for this functionality 2. Develop the functionality according the requirements 3. Test the functionality according the requirements | The admin can add new plugins and widgets without significant changes in the existent design | Fail | The requirement is incomplete and ambiguous: there are too many different plugins and widgets now and could be even more in the nearest future. It is needed to specificate requirements first, what exact plugins and widgets are needed.
320 | High | Ckeck if the CMS can provide content updating without involving developers | 1. Open the portal CMS 2. Check if the admin has access to the content updating functions 3. Update some content 4. Check if the content updated successfully | The admin can provide content updating by CMS without involving developers | Blocked | There is no access to the admin panel
321 | High | Ckeck if the multimedia content is integrated and could be updated by admin | 1. Open the portal CMS 2. Check if the admin has access to the multimedia content updating 3. Update some content adding video, sound and image 4. Check if the content updated successfully | Multimedia content is integrated and could be updated by admin | Blocked | There is no access to the admin panel

## Frontend
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
401 | Medium | Check if a server-side caching is implemented and active | 1. Open https://seositecheckup.com/seo-audit/page-cache-test-server-side-caching/ 2. Put the adress https://prometheusqastage1.wixsite.com/skybot 3. Choose the server-side caching test 4. Get the answer | server-side caching is implemented and active | Pass
402 | Medium | Check if a CDN is implemented and active for serving static content using Postman | 1. Create and pull a request Get in Postman with https://prometheusqastage3.wixsite.com/skybot adress 2. Check the CDN in the Body of the page | CDN is used | Pass
403 | Medium | Check if a html-cacheable is implemented and active with the Postman tool | 1. Create and pull a request Get in Postman with https://prometheusqastage3.wixsite.com/skybot adress 2. Check the Html-cacheable parametr is true | The Html-cacheable parametr is true | Pass
404 | Medium | Ensure asynchronous loading of resources to prioritize main page content | 1. Open the portal https://prometheusqastage3.wixsite.com/skybot adress 2. Check the loading progress by browser Dev Tools | Asynchronous loading is present | Pass
405 | Medium | Ensure Lazy Loading technology is used | 1. Open the portal https://prometheusqastage3.wixsite.com/skybot adress 2. Check the loading progress by browser Dev Tools | Lazy Loading technology is present | Pass
406 | Medium | Ensure Load balancing is used to distribute the load of the requests between servers | 1. Open the hosting admin panel of the portal 2. Check the Load balancing is present and turned on | Load balancing is used to distribute the load of the requests between servers | Blocked | There is no access to the admin panel
407 | High | Check if the portal works with proper visual displaying under Windows 10/11 using Chrome browser | 1. Open the site under Windows OS 10/11, using Chrome 2. Observe the site main pages view, elements positioning, correct design and scale showing 3. Observe the site elements functionality | Site is opened, the visual display is correct, scaling works, main pages with functional elements are available | Pass
408 | High | Check if the portal works with proper visual displaying under Windows 10/11 using Firefox browser | 1. Open the site under Windows OS 10/11, using Firefox 2. Observe the site main pages view, elements positioning, correct design and scale showing 3. Observe the site elements functionality | Site is opened, the visual display is correct, scaling works, main pages with functional elements are available | Pass
409 | Low | Check if the portal works with proper visual displaying under Windows 10/11 using Safari browser (native) | 1. Open the site under Windows 10/11 using Safari browser (native) 2. Observe the site main pages view, elements positioning, correct design | Site is opened, the visual display is correct, scaling works, main pages with functional elements are available | Pass
410 | High | Check if the portal works with proper visual displaying under Linux 24/25 using Firefox browser | 1. Open the site under Linux 24/25 using Firefox browser 2. Observe the site main pages view, elements positioning, correct design and scale showing 3. Observe the site elements functionality | Site is opened, the visual display is correct, scaling works, main pages with functional elements are available | Pass
411 | High | Check if the portal works with proper visual displaying under Linux 24/25 using Chrome browser | 1. Open the site under Linux 24/25 using Chrome browser 2. Observe the site main pages view, elements positioning, correct design and scale showing 3. Observe the site elements functionality | Site is opened, the visual display is correct, scaling works, main pages with functional elements are available | Pass
412 | High | Check if the portal works with proper visual displaying under Mac OS 14/15 using Safari browser | 1. Open the site under Mac OS 14/15 using Safari browser 2. Observe the site main pages view, elements positioning, correct design and scale showing 3. Observe the site elements functionality | Site is opened, the visual display is correct, scaling works, main pages with functional elements are available | Pass
413 | Medium | Verify if XSS and CSRF defence is used on the portal | 1. Visit https://pentest-tools.com/website-vulnerability-scanning/xss-scanner-online and enter https://prometheusqastage3.wixsite.com/skybot adress 2. Check the XSS 3. Check the CSRF | The XSS and CSRF defence is present | Pass
414 | Medium | Check if the authentication mechanism on the portal ensured the security of user data | 1. Ask the dev team if the authentication mechanism on the portal ensured the security of user data and how 2. Check the reports and documentation about authentication mechanism on the portal | The authentication mechanism on the portal ensured the security of user data | Blocked | No access to the Portal output data and documentation
415 | Medium | Check if the SAST is implemented in the SDLC of the portal | 1. Ask the dev team the SAST reports and documentation 2. Check the reports and documentation | SAST is implemented in the SDLC of the portal | Blocked | No access to the Portal output data and documentation
416 | Medium | Check if the DAST check of the portal is provided | 1. Ask the dev team the DAST reports and documentation 2. Check the reports and documentation | DAST check of the portal is provided | Blocked | No access to the Portal output data and documentation
417 | Low | Verify if WCAG recommendations and ARIA attributes are implemented | 1. Visit the test tool https://wave.webaim.org , put the porta's adress https://prometheusqastage3.wixsite.com/skybot 2. Verify compliance with WCAG and ARIA according to the WCAG recommendations and ARIA attributes | WCAG recommendations and ARIA attributes are implemented | Fail | WCAG recommendations and ARIA attributes are not implemented
418 | Low | Check the feedback about frontend from users | 1. Check the feedback from the portal users | The feedback about frontend from users is realized and works correctly, feedbacks are collecting | Fail | The feedback from users is not realized yet
419 | Medium | Check if the interface is intuitive and understandable for users | 1. Check the user's account options and design 2. Check the user's path to provide main actions 3. Check the site navigation, functional elements and names of the user's options are understandable | The interface is intuitive and understandable for users | Pass

## Backend
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
501 | Medium | Check if the monitoring system Prometheus with Graffana addon is implemented | 1. Ask the dev team the Prometheus access 2. Check the Graffana addon is present 3. Check if the Prometheus is adjusted and provided on the portal | The monitoring system Prometheus with Graffana addon is implemented | Blocked | No access to the Portal output data and documentation
502 | Medium | Check if the logging of all requests, responses, errors and mistakes is implemented | 1. Access the admin panel 2. Check the logs of requests, responses, errors and mistakes and it's adjustment | The logging of all requests, responses, errors and mistakes is implemented | Blocked | There is no access to the admin panel
503 | Medium | Verify the automated regression tests are implemented to test the system after updates and functional changes | 1. Ask the dev team the automated regression tests, its adjustment and documentation 2. Check tests and reports | The automated regression tests are implemented to the system | Blocked | No access to the Portal output data and documentation
504 | High | Verify if the CI/CD is implemented | 1. Ask the dev team if the CI/CD is implemented 2. Check the CI/CD adjusted and works | The CI/CD is implemented to the system | Blocked | No access to the Portal output data and documentation
505 | High | Verify if the provider backing up the server's data automatically | 1. Ask the hosting provider if backing up the server's data automatically is available | Backing up the server's data automatically is available | Blocked | There is no access to the hosting admin panel
506 | Medium | Verify the repair plan in case of failure or data loss is ready | 1. Ask the dev team the the repair plan 2. Check the repair plan is completed | The repair plan in case of failure or data loss is ready | Blocked | No access to the Portal output data and documentation
507 | High | Check if SSL is used on the web-site | 1. Create and pull a request Get in Postman with https://prometheusqastage3.wixsite.com/skybot adress 2. Turn on the SSL certificate verification | SSL certification is present | Pass
508 | Low | Check if the server decomposition is used on the portal | 1. Access the admin panel of hosting 2. Check the server decomposition option | Server decomposition is used on the portal | Blocked | There is no access to the hosting admin panel
509 | Low | Check if the automatic scaling mechanism is used to optimize the server load | 1. Access the admin panel of hosting 2. Check the automatic scaling option | Automatic scaling mechanism is used to optimize the server load | Blocked | There is no access to the hosting admin panel
510 | Medium | Ensure that multi-factor authentication is enabled for administrative access to the web portal and servers | 1. Attempt to log in to the administrative portal with a valid username and password. 2. Verify if an additional authentication step (e.g., SMS code, app-based token) is required | Administrative access should require multi-factor authentication, adding an extra layer of security | Blocked | There is no access to the admin panel
511 | Medium | Ensure that access to administrative areas is restricted based on IP addresses | 1. Attempt to access the administrative portal from an unauthorized IP address. 2. Attempt to access the administrative portal from an authorized IP address. | Access to administrative areas is based only on authorized IP address | Blocked | There is no access to the admin panel
512 | Medium | Verify if the tech support is available 24/7 on the portal hosting | 1. Ask the hosting provider if the tech support is available 24/7 on the portal hosting | Tech support is available 24/7 on the portal hosting | Blocked | There is no access to the hosting admin panel
513 | Medium | Verify the detailed documentation about adjustment and using the backend-services is present | 1. Ask the dev team the detailed documentation about adjustment and using the backend-services 2. Check the documentation if it is completed in adjustment and using the backend-services | Detailed documentation about adjustment and using the backend-services is present | Blocked | No access to the Portal output data and documentation

## Purchase
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
601 | High | Verify that the order process is completed on a single page | 1. Add a product to the cart. 2. Proceed to checkout. 3. Complete all steps (enter customer information, shipping details, and payment information) on the same page. 4. Submit the order. | The order is completed on a single page, and a confirmation message is displayed | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
602 | High | Verify that the order process has minimal and clearly defined steps | 1. Add a product to the cart. 2. Proceed to checkout. 3. Observe the number of steps displayed (e.g., customer information, shipping, payment). | The order process has clearly defined and minimal steps | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
603 | High | Verify if the registered user is able to make a standard order of product | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Log in 3. Visit product page 4. Click Order button 5. Fill in the Order form with valid data and contacts 6. Receive the confirmation of order | The registered user is able to make a standard order of product | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
604 | High | Verify if the registered user is able to make a fast order (all ordering operations on the one page) | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 3. Do the fast order | The fast order is available on the one page | Fail | There is no Fast order option on the product page User can use the Fast order button on the product page, but as a result there is a message: "We can't accept online orders right now". Checkout function is not ready.
605 | Medium | Verify the use of autocomplete and hints for user information fields | 1. Log in to the user account. 2. Add a product to the cart. 3. Proceed to checkout. 4. Enter partial information in user fields (e.g., start typing the address). 5. Observe the autocomplete suggestions and hints. | Fields are autocompleted based on previously entered data, and hints are provided to assist the user | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
606 | High | Verify if the user is able to make an order without registration | 1. Add a product to the cart. 2. Proceed to checkout. 3. Select the guest checkout option. 4. Enter the necessary information and complete the purchase | The user is able to order without registration | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
607 | High | Verify if the user is able to have messages about invalid data when entered incorrect information | 1. Visit the https://prometheusqastage3.wixsite.com/skybot 2. Enter an incorrect format of contact info in the order 3. Check the system message | The user is able to have message about incorrect data in the order | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
608 | High | Verify that the order forms are mobile-friendly and easy to use | 1. Access the web portal on a mobile device. 2. Add a product to the cart. 3. Proceed to checkout. 4. Fill out the forms using the mobile device. | Forms are easy to fill out on a mobile device, with no usability issues | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
609 | High | Verify that the system immediately checks for errors and provides feedback | 1. Add a product to the cart. 2. Proceed to checkout. 3. Enter incorrect data in a field (e.g., invalid email format). 4. Observe the system’s response. | The system immediately highlights errors and provides feedback for corrections | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
610 | High | Verify that the user can review the order summary before confirming the purchase | 1. Add a product to the cart. 2. Proceed to checkout. 3. Review the order summary, including items, quantities, prices, and total amount. 4. Confirm the order. | The user can review and confirm the order summary before completing the purchase | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
611 | High | Verify that the user can easily modify the cart contents without restarting the order process | 1. Add multiple products to the cart. 2. Proceed to checkout. 3. Modify the numbers or remove items from the cart. 4. Confirm the changes and proceed | The user can easily modify the cart contents without returning to the initial steps | Fail | User can add the product to the cart and view the cart, and change the number of the product in cart, and can return to the catalog and add another product but if the user will delete all products exept the last and will try to delete the last one, he will get the 401 error. Also checkout is not ready, there is a message: "We can't accept online orders right now"
612 | Medium | Verify the presence of a progress bar that indicates the current stage of the checkout process | 1. Add a product to the cart. 2. Proceed to checkout. 3. Observe the progress bar indicating the current stage (e.g., customer information, shipping, payment). | The progress bar correctly indicates the current stage and remaining steps | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
613 | High | Verify that the payment process uses a secure connection (SSL/TLS) | 1. Add a product to the cart. 2. Proceed to checkout. 3. Enter payment details. 4. Check for SSL/TLS indicators by Dev Tools in the browser | The payment process uses a secure connection, indicated by the SSL/TLS certificate | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
614 | High | Verify that the system offers multiple reliable payment options | 1. Add a product to the cart. 2. Proceed to checkout. 3. Observe the available payment options (e.g., Visa and Mastercard credit cards, PayPal, Google Pay, Apple Pay). | Multiple reliable payment options are available | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
615 | Medium | Verify that the system sends an order confirmation email with details after purchase | 1. Complete an order. 2. Check the email inbox for the order confirmation email | An order confirmation email with order details is received | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
616 | Medium | Verify that the system displays a confirmation page with order details after the purchase | 1. Complete an order. 2. Observe the confirmation page displayed | The confirmation page displays all necessary order details | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
617 | High | Verify that the live chat is available on the portal and user can request support when making a purchase | 1. Navigate to the portal. 2. Check for the presence of the live chat. 3. Navigate to the product catalog page. 4. Check for the presence of the live chat. 5. Navigate to a product details page. 6. Check for the presence of the live chat. | The live chat is available on all needed pages and user can request support when making a purchase | Pass
618 | Medium | Verify if the user is able to request the user's support | 1. Navigate to the homepage. 2. Fill in the support form with valid contacts 3. Send the request 4. Check if the confirmation of your support request is received | The user is able to request the user's support | Fail | Is it possible to visit support page and fill in the support form, and the system shows message: "thank you for your request", but the confirmation is not working. The function on the site is not ready
619 | High | Verify if the registered user is able to make a purchase by mobile device | 1. Visit the https://prometheusqastage3.wixsite.com/skybot from mobile device 2. Log in 3. Visit product page 4. Click Order button 5. Fill in the Order form with valid data and contacts 6. Receive the confirmation of order | The registered user is able to make a purchase by mobile device | Fail | User can add the product to the cart and view the cart, but when user need to proceed and checkout, there is a message: "We can't accept online orders right now". Checkout function is not ready.
620 | High | Verify if elements of the mobile interface are big enough to use on the little screen by making the purchase | 1. Open the portal https://prometheusqastage3.wixsite.com/skybot using the smartphone 2. Check elements of the interface in the Purchase process if they are big enough to purchase comfortable | The interface are big enough to use on the little screen by making the purchase | Pass

## Security
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
701 | High | Verify the strong passwords with min symbols lenght, including different types of symbols is required for user registration and password applying | 1. Ask the dev team if the strong passwords with min symbols lenght, including different types of symbols is required for user registration and password applying and how 2. Check the documentation about authentication mechanism on the portal | the strong passwords with min symbols lenght, including different types of symbols is required for user registration and password applying | Blocked | No access to the Portal output data and documentation
702 | Medium | Ensure that 2-factor authentication option is available for users | 1. Navigate to the portal 2. Log in and enter the user's account 3. Check the 2-factor authentication option | 2-factor authentication option is available for users | Fail | There is no option of 2-factor autentication in the user's account
703 | High | Check if SSL is used on the web-site | 1. Create and pull a request Get in Postman with https://prometheusqastage3.wixsite.com/skybot adress 2. Turn on the SSL certificate verification | SSL certification is present | Pass
704 | Medium | Verify if XSS and CSRF defence is used on the portal | 1. Visit https://pentest-tools.com/website-vulnerability-scanning/xss-scanner-online and enter https://prometheusqastage3.wixsite.com/skybot adress 2. Check the XSS 3. Check the CSRF | The XSS and CSRF defence is present | Pass
705 | High | Check if SSL is used in payment process | 1. Purchase a product on the portal 2. Proceed to checkout 3. Check whether the connection is https and the SSL certificate is actual | SSL certification is present in payment process | Blocked | Checkout page is not ready
706 | Medium | Check the PCI DSS is provided on the portal | Check the PCI DSS certificate | PCI DSS is provided on the portal | Blocked | No access to the Portal output data and documentation
707 | Medium | Check if the monitoring safety system is integrated | 1. Ask the dev team if the monitoring safety system is integrated and how 2. Check the documentation about the monitoring safety system on the portal | Monitoring safety system is integrated | Blocked | No access to the Portal output data and documentation
708 | Low | Check if the automated notifications about alerts and suspicious activity are adjusted | 1. Ask the dev team if the automated notifications about alerts and suspicious activity are adjusted 2. Check the documentation about automated notifications on the portal | Automated notifications about alerts and suspicious activity are adjusted | Blocked | No access to the Portal output data and documentation
709 | Medium | Verify if the user is able to get acquainted with Privacy policy on the portal | 1. Navigate to the Store Policies page 2. Check the Privacy policy text | User is able to get acquainted with Privacy policy on the portal | Pass
710 | Medium | Verify that the portal complies with GDPR requirements for storing and processing personal data | 1. Navigate to the Store Policies page 2. Check the Privacy policy text | Portal complies with GDPR requirements for storing and processing personal data | Pass

## Product page
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
801 | High | Verify that the product page displays complete detailed information about the electric vehicle model | 1. Navigate to the product page of a specific electric vehicle. 2. Check that the page displays the full model name. 3. Check the technical characteristics (weight, dimensions, battery type, range on a single charge, charging time, etc.). 4. Check the features and other important information. 5. Verify the category of the vehicle by type of transport. | The page should display all detailed information, including the full model name, technical characteristics, features, and category of the vehicle | Pass
802 | Medium | Verify that the product page displays pictures and videos of the product | 1. Navigate to the product page of a specific electric vehicle. 2. Check that there are multiple pictures of the product. 3. Verify that there are videos of the product. | The page should display multiple pictures and videos of the product | Pass
803 | Medium | Verify that the product page shows the position of the product in the product groups and subgroups | 1. Navigate to the product page of a specific electric vehicle. 2. Check that the page displays the product's position in product groups and subgroups. | The page should display the product's position in its groups and subgroups | Pass
804 | High | Verify that users can add the product to cart from the product page | 1. Navigate to the product page of a specific electric vehicle. 2. Click on the "Order" button | The product should be added to the shopping cart, and the user should be redirected to the checkout page | Pass
805 | High | Verify that users can use the "Fast Order" option from the product page | 1. Navigate to the product page of a specific electric vehicle. 2. Click on the "Fast order" button" | The fast order should be processed and the user should be redirected to the checkout page | Pass
806 | Medium | Verify that users can review the product | 1. Log in to the user account. 2. Navigate to the product page of a specific electric vehicle. 3. Click on the "Review Product" button. 4. Write a review and submit it. | The review should be posted and displayed on the product page | Pass
807 | Low | Verify if the user is able to add a video review to the product content | 1. Log in to the user account. 2. Navigate to the product page of a specific electric vehicle. 3. Click on the "Review Product" button. 3. Make a review of the product adding the video from the supported video hosting and submit it 4. Check if the video is showed on the product page | The user is able to add a video review to the product content | Pass
808 | Low | Verify that pictures on the product page are clickable and can be zoomed | 1. Navigate to the product page of a specific electric vehicle. 2. Click on a product picture. 3. Use the zoom feature to enlarge the picture | The picture should be clickable and should open in a zoom view | Pass
809 | Low | Verify that videos on the product page can be played | 1. Navigate to the product page of a specific electric vehicle. 2. Click on a video to play it. | The video should play | Pass

## Test-drive
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
901 | High | Verify that the user can view a list of available electric vehicle models for test drives with a short description of each model | 1. Navigate to the test drive page. 2. Check for the presence of a list of available electric vehicle models. 3. Verify that each model in the list has a short description. | The user sees a list of available electric vehicle models, each with a short description | Fail | Test-drive function is not ready
902 | High | Verify that the user can select a model from the list of available models for a test drive | 1. Navigate to the test drive page. 2. Click on a model from the list of available models. 3. Verify that the selected model is highlighted or marked as selected | The user can select a model, and the selected model is highlighted or marked | Fail | Test-drive function is not ready
903 | High | Verify that the user can choose a date and time for the test drive from an availability calendar | 1. Navigate to the test drive page. 2. Select a model for the test drive. 3. Open the availability calendar. 4. Choose a date and time for the test drive | The user can select a date and time for the test drive from the availability calendar | Fail | Test-drive function is not ready
904 | High | Verify that the user can fill in personal information (name, contact details) required for the test drive booking | 1. Navigate to the test drive page. 2. Select a model and choose a date and time. 3. Enter personal information in the provided fields (name, contact phone, email). | The user can successfully enter their personal information | Fail | Test-drive function is not ready
905 | High | Verify that the user can submit the test drive booking and receive a confirmation | 1. Navigate to the test drive page. 2. Fill in all required information and choose a date and time. 3. Click the "Submit" button. 4. Check for a confirmation message or email | The test drive booking is submitted successfully, and the user receives a confirmation message or email | Fail | Test-drive function is not ready
906 | Medium | Verify that the user receives an automatic confirmation email after submitting the test drive booking | 1. Submit a test drive booking. 2. Check the email inbox for a confirmation email | The user receives a confirmation email with details of the test drive booking | Fail | Test-drive function is not ready
907 | Low | Verify that the user receives a reminder email a few days or hours before the scheduled test drive | 1. Submit a test drive booking. 2. Wait for the scheduled reminder period (a few days or hours before the test drive). 3. Check the email inbox for a reminder email | The user receives a reminder email before the scheduled test drive | Fail | Test-drive function is not ready
908 | Medium | Verify that the user can view instructions and conditions for the test drive | 1. Navigate to the test drive page. 2. Look for a section with instructions and conditions for the test drive | The user can view detailed instructions and conditions for the test drive | Fail | Test-drive function is not ready
909 | Low | Verify that the user can view contact information for support regarding the test drive | 1. Navigate to the test drive page. 2. Look for a section with contact information | The user can view contact information for test drive support | Fail | Test-drive function is not ready
910 | Medium | Verify that the portal complies with GDPR requirements for storing and processing personal data | Navigate to the test drive page. Check for a privacy policy or data protection notice. Review the provided information to ensure compliance with GDPR | The portal provides a privacy policy or data protection notice that complies with GDPR requirements | Fail | Test-drive function is not ready

## Service booking
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
1101 | High | Verify that the system collects personal information (name, contact details) during service booking | 1. Authenticate and navigate to the service booking page. 2. Fill in personal information fields (name, contact phone, email). 3. Proceed to the next step | The system collects and validates the entered personal information | Fail | After the service is selected system shows message: "Sorry, this service is not yet available for online bookings. Please contact us for more information." The function is not ready
1102 | High | Verify that the user can select a service center location | 1. Authenticate and navigate to the service booking page. 2. View the list of available service centers. 3. Select a preferred service center location | The user can view and select a service center from the list | Fail | After the service is selected system shows message: "Sorry, this service is not yet available for online bookings. Please contact us for more information." The function is not ready
1103 | Medium | Verify that the user can choose the type of service (e.g., maintenance, repair, warranty service) | 1. Authenticate and navigate to the service booking page. 2. View the list of service types. 3. Select a type of service from the list | The user can view and select a type of service | Fail | After the service is selected system shows message: "Sorry, this service is not yet available for online bookings. Please contact us for more information." The function is not ready
1104 | Medium | Verify that the user can describe the issue or fault with their vehicle | 1. Authenticate and navigate to the service booking page. 2. Select a service type. 3. Enter a description of the issue or fault in the provided text field | The user can enter and submit a description of the issue or fault | Fail | After the service is selected system shows message: "Sorry, this service is not yet available for online bookings. Please contact us for more information." The function is not ready
1105 | High | Verify that the user can submit the service booking and receive a confirmation | 1. Authenticate and navigate to the service booking page. 2. Fill in personal information, select service center, choose service type, and describe the issue. 3. Click the "Submit" button. 4. Check for a confirmation message or email | The service booking is submitted successfully, and the user receives a confirmation message or email | Fail | After the service is selected system shows message: "Sorry, this service is not yet available for online bookings. Please contact us for more information." The function is not ready
1106 | Low | Verify that the user receives a reminder email or SMS before the service appointment | 1. Submit a service booking. 2. Wait for the reminder period (a day or hour before the appointment). 3. Check the email inbox or SMS for a reminder | The user receives a reminder email or SMS before the scheduled service appointment | Fail | After the service is selected system shows message: "Sorry, this service is not yet available for online bookings. Please contact us for more information." The function is not ready
1107 | Medium | Verify that the portal complies with GDPR requirements for storing and processing personal data | Navigate to the test drive page. Check for a privacy policy or data protection notice. Review the provided information to ensure compliance with GDPR | The portal provides a privacy policy or data protection notice that complies with GDPR requirements | Fail | There is no GDPR requirements for storing and processing personal data on the Service Booking page

## Reviews
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
1201 | High | Verify that users can review and rate the product | 1. Log in to the user account. 2. Navigate to the product page of a specific electric vehicle. 3. Click on the "Review Product" button. 4. Rate the product 5. Write a review and submit it. | The review and rate should be posted and displayed on the product page | Pass
1202 | Medium | Verify if the user is able to add a video review to the product content | 1. Log in to the user account. 2. Navigate to the product page of a specific electric vehicle. 3. Click on the "Review Product" button. 3. Make a review of the product adding the video from the supported video hosting and submit it 4. Check if the video is showed on the product page | The user is able to add a video review from the supported video hosting to the product content | Fail | Video adding is realised by uploading the video file from the user's device, also images are possible to upload. But the integration with video hosting is absent.
1203 | Low | Verify that non-registered users who doesn't purchased or rented the product can't leave the review and rate the product | 1. Log out from the user account. 2. Navigate to the product page of a specific electric vehicle that was not purchased or rented by test user 3. Click on the "Review Product" button. 4. Put some random non-valid email 5. Rate the product 6. Write a review and submit it. | Non-registered users who doesn't purchased or rented the product can't leave the review and rate the product | Fail | Every user can leave a review and rate the product, even non-registered
1204 | Medium | Verify the moderation of the reviews is available by admin | 1. Enter the admin panel of the portal 2. Check the reviews moderation option | The moderation of the reviews is available by admin | Blocked | There is no access to the admin panel
1205 | Medium | Verify the portal or the brand owners can answer the reviews | 1. Enter the admin panel of the portal 2. Check the portal owners and brand owners admin accounts have the option to answer the reviews | The portal or the brand owners can answer the reviews | Blocked | There is no access to the admin panel
1206 | Low | Verify that the filter to block unacceptable reviews is provided on the portal | 1. Enter the admin panel of the portal 2. Check the filter to block unacceptable reviews and option to adjust it | The filter to block unacceptable reviews is provided on the portal | Blocked | There is no access to the admin panel
1207 | Medium | Verify if the product rate is shown on the product page and on the shop page | 1. Log in to the user account. 2. Navigate to the product page of a specific electric vehicle. 3. Navigate to the shop page 4. Check the product rate | The product rate is shown on the product page and on the shop page | Pass
1208 | Low | Verify if the user can sort the reviews by date, rate or usefulness | 1. Navigate to the product page of a specific electric vehicle. 2. Check the sorting reviews by date, rate or usefulness | Еhe user can sort the reviews by date, rate or usefulness | Pass
1209 | Medium | Verify that the portal complies with GDPR requirements for storing and processing personal data when the user is making the review | 1. Navigate to the review form of the product page of a specific electric vehicle 2. Check for a privacy policy or data protection notice. 3. Review the provided information to ensure compliance with GDPR | The portal provides a privacy policy or data protection notice that complies with GDPR requirements when the user is making the review | Fail | There is no GDPR requirements for storing and processing personal data when the user is making the review

## Recommendations
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
1301 | High | Verify that the personalized profile of the user is provided on the portal by collecting the data about viewed products, orders, reviews etc | 1. Ask the dev team if the personalized profile of the user is provided on the portal and how 2. Check the reports and documentation about users data collecting | The personalized profile of the user is provided on the portal | Fail | This feature is not ready
1302 | Medium | Verify that the machine learning algorithm is used for users data analyzing and recommendations generating | 1. Ask the dev team if the machine learning algorithm is used for users data analyzing and recommendations generating 2. Check the reports and documentation about machine learning algorithm | The machine learning algorithm is used for users data analyzing and recommendations generating | Fail | This feature is not ready

## Videos
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
1401 | High | Verify that Youtube video hosting is integrated by API | 1. Navigate to the video reviews page 2. Check the videos from Youtube | Youtube video hosting is integrated by API | Pass
1402 | High | Verify that videos on the portal can be played | 1. Navigate to the product page of a specific electric vehicle. 2. Click on a video to play it. | The video should play | Pass
1403 | Medium | Verify that the user can rate and review the videos on the portal | 1. Navigate to the video reviews page 2. Rate and review the video | The users can rate and review the videos on the portal | Fail | There is no such option to rate or to review the videos
1404 | Low | Verify that the user can search the video reviews by key words or filter the video reviews by product categories | 1. Navigate to the video reviews page 2. Search the video reviews by key words 3. Filter the video reviews by product categories | The user can search the video reviews by key words or filter the video reviews by product categories | Fail | There is no such option to search or to filter the videos
1405 | High | Verify that the user can view video reviews on the mobile version of the portal | 1. Navigate to the product page of a specific electric vehicle by mobile device 2. Click on a video to play it. | The video should play | Pass
1406 | Medium | Verify that the video reviews on the portal complies with GDPR requirements for storing and processing personal data when the user is making the review | 1. Navigate to the video reviews page 2. Check for a privacy policy or data protection notice for users that are using the video service 3. Review the provided information to ensure compliance with GDPR | The portal provides a privacy policy or data protection notice that complies with GDPR requirements when the user is watching the videos | Fail | There is no GDPR requirements for storing and processing personal data when the user is watching the videos

## Analytics
Test ID | Priority | Description | Test Steps | Expected Result | Actual Result | Comments
1501 | High | Verify if the analitycs platform is integrated on the portal by API | 1. Ask the dev team if the analitycs platform is integrated on the portal by API and how 2. Check the reports and documentation about analitycs API integration |  | Blocked | No access to the Portal output data and documentation

## Summary
Summary of the acceptance test, divided by sections of requirements
Requirement section | Tests passed | Tests failed | Tests blocked | Issues and recommendations
Web hosting | 14/22 | 0/22 | 8/22 | Access to the hosting admin panel and hosting provider info is needed to check blocked tests. All other indicators meets the requirements.
Mobile version | 10/16 | 6/16 | 0/16 | In horizontal screen orientation the portal has many issues, elements of the interface are not adopting correctly on different screen sizes. Also portal needs to improve performance by optimization
Design | 3/21 | 13/21 | 5/21 | There is a list of recommendations to fix the visual perception and usability of the portal. There is ambiguity about main page name and content. Adaptation to defferent sceen sizes and inclusivity is also not ready. User's feedback and usability testing with users was not provided.
Frontend | 13/19 | 2/19 | 4/19 | Access to the Portal output data and documentation info is needed to check blocked tests. Also WCAG recommendations, ARIA attributes and User's feedback are not implemented
Backend | 1/13 | 0/13 | 12/13 | Access to the hosting admin panel, portal admin panel, portal output data and documentation is needed to check blocked tests. All other indicators meets the requirements.
Purchase | 2/20 | 18/20 | 0/20 | Checkout function with payments and mail confirmation are not ready. All other indicators meets the requirements.
Security | 2024-10-04 | 2024-10-01 | 2024-10-05 | Access to the Portal output data and documentation info is needed to check blocked tests. There is no option of 2-factor autentication in the user's account. All other indicators meets the requirements.
Product page | 2024-09-09 | 0/9 | 0/9 | All indicators meets the requirements.
Test-drive | 0/10 | 2024-10-10 | 0/10 | Test-drive function is not ready
Service booking | 0/7 | 2024-07-07 | 0/7 | Service booking function is not ready
Reviews | 2024-09-03 | 2024-09-03 | 2024-09-03 | Access to portal's admin panel is needed to check blocked tests. Video reviews are realised as a video upload from the user's device, but not as video hosting integration, Also there is no stop for non-registered users to leave the reviews. All other indicators meets the requirements.
Recommendations | 0/2 | 2024-02-02 | 0/2 | Recommendations function is not ready
Videos | 2024-06-03 | 2024-06-03 | 0/6 | Video hosting is integrated, but user can't review, search and sort the videos
Analytics | 0/1 | 0/1 | 2024-01-01 | Access to the Portal output data and documentation info is needed to check blocked tests.
Total | 62/165 | 65/165 | 38/165
| 38% | 39% | 23%
Readiness assessment | The portal is not ready for release. Many functions are not ready, some of features are needed to be fixed and also access to all needed tools and documentations is needed to provide the next iteration of the Acceptance test. Mostly bugs can be fixed without non-realised functionality. The recommendation is to provide bugs fixing, open the necessary access and retest.